## DAR
1) Decision Analysis & Resolution for selecting Agile Development Methodologies for PMS NOIDA Authority project
Date | 2016-04-07
Criteria | Vishal Shukla | Dhananjay | Client
Cost Factor | Yes | Yes | Yes
Customer Requirments | Yes | Not Elobrated in details In RFP | Yes
Requirement Freeze | NO | NO | Can be chnaged
Phase-Wise Requirements | Yes | Yes | Yes
DAR Selection Criteria
Selection Criteria | Cost Factors | Customer Req | Req. Freeze | Phase-Wise Requirements
Alternatives | Waterfall | Sprial | Waterfall | Agile
Evaluation Method | Client Requirement & Bucket Decision
Evaluation Result: Based on Phase wise requirements and Government project (bucket) it was decided thet Agile Development Methodlogies will followed in this project.
2) Decision Analysis & Resolution for PMS NOIDA Authority project for Selecting development technology
Date | 2016-04-07
Criteria for Technology | Vishal Shukla | Dhananjay | Taraknath | Client
ASP.NET | Yes | Yes | Yes | Yes
VB.NET | No | No | No | Yes
JAVA | No | No | No | No
DAR Selection Criteria
Selection Criteria | Cost Factors | Customer Req | Resource Competency | Client System Earlier
Alternative 1 | Java | ASP.NET | PHP | ASP.NET
Evaluation Method for programming language | Client Decision |  | Client has .NET development earlier and decided to develop in same technology
Evaluation Result: Based on client decision, We have chosen ASP.NET for programming language and for reporting services SQL Databse will be used
3) Decision Analysis & Resolution for implementing Process Management tool in PMS NOIDA Authority project for Innovation and for Application Development using TFS
Date | 2016-04-07
Criteria for Process | Vishal Shukla | Dhananjay | Client
Automation | NO | Yes | Yes
Manual | Yes | No | NO
Criteria for Application Development | Vishal Shukla | Dhananjay | Client
TFS | Yes | Yes | Yes
VSS | NO | NO | NO
DAR Selection Criteria
Selection Criteria for Process | Process Innovation in New Project |  | CMMIL4 & L5 Requiremets |  | User Firendly
Alternative | Timelive | IQMS | Time Live | IQMS | IQMS | Timelive
Selection Criteria for TFS | Check-in Check-out with server workspaces |  |  | Edit Commit with local workspaces |  |  | Test Management
Alternative | TFS | GIT | VSS | TFS | GIT | VSS | TFS | GIT | VSS
Evaluation Method for programming language | Technology Competencies, Better Configuration Management and Mangement decision
Evaluation Result1: Based on requirement of CMMI L4 & L5 and for Process innovation, NOIDA project selected for implementing Process Automation tool (IQMS)
Evaluation Result2: Based on Integrated combination of version Control, work item (requirements/Bug) tracking, planning, Test management, Reporting etc. management has selected TFS for Application development