## RACI Matrix
RACI Matrix | Noida Authority-Property Management System
| Customer | Management | Program Manager | Crown | Project Manager Digitization & Analytics | Project Manager Application Development | Business Analyst | Database Adminstrator | Technical Architect | Lead Developer | Test Manager | QA Lead | Infrastructure | Configuration Manager
Initiate Phase Activities
INI - Kick Off |  | A | R |  |  | C | I |  | I | I | I | C | I | I
INI - Prepare PMP |  | I | C |  |  | R | I | I | I | I | R | C | I | I
INI - Approve PMP |  | I | A |  |  | R | I | I | I | I | I | I | I | I
Project Management
Project Monitoring & Control |  | I | A |  |  | R | I | I | I | I | I |  | I | I
Risk Management |  | I | A |  |  | R | I | I | I | I | I |  | I | I
Dizitization &Scanning |  | I | I | R | A |  | I | I | I
Data Entry |  | I | I | R | A |  | I | I | I
Weekly Project Review & Status Report
Plan Phase Activities
REQ - SRS Prepare |  | I | C |  |  | C | R |  | C | I | I |  | I | I
REQ - SRS Review |  | I | R |  |  | A | C |  | C | I | I |  | I | I
REQ - SRS Approve | R | A | I |  |  | I | I |  | I | I | I |  | I | I
Design Phase Activities
DES - Design Prepare |  | I | C |  |  | A | C |  | R | I | I |  | I | I
DES - Design Review |  | I | C |  |  | R | C |  | R | I | I |  | I | I
DES - Design Approve |  | I | A |  |  | C | C |  | R | I | I |  | I | I
Database Design (Structure) | I | I | C |  | A |  |  | R
Coding Phase Activities
COD - Coding |  | I | I |  |  | A | I |  | C | R
COD - Code Review | [5 empty] | A |  |  |  | R | I
COD - Unit Testing | [5 empty] | A |  |  |  | R
Testing Phase Activities
Quality Magament Plan | [5 empty] | I | I |  | I | I | A
Product Quality | [5 empty] | A |  |  |  | R | I
Process Quality | [5 empty] | A |  |  |  |  | R
Product Audit
Process Audit
Release Phase Activities
Build & Release Plan | [5 empty] | A |  |  |  |  | R
REL - Deployment/Installation | [5 empty] | A |  |  |  | R
Configuration Management
CON - Configuration Management Plan | [5 empty] | A | [7 empty] | R
Configuration Audit
Close Phase Activities
CLO - Complete Project Closure | I | A | A |  |  | R
Scanning & Digitization
INI - Kick Off
INI - Prepare PMP
INI - Approve PMP |  |  |  |  | Requirement Gathring
Requirement Signoff
Project Management |  |  |  |  | Data Entry
Project Monitoring & Control
Risk Management
Dizitization &Scanning
Data Entry
Weekly Project Review & Status Report
Plan Phase Activities
REQ - SRS Prepare
REQ - SRS Review
REQ - SRS Approve
Design Phase Activities
DES - Design Prepare
DES - Design Review
DES - Design Approve
Database Design (Structure)
Coding Phase Activities
COD - Coding
COD - Code Review
COD - Unit Testing
Testing Phase Activities
Quality Magament Plan
Product Quality
Process Quality
Product Audit
Process Audit
Release Phase Activities
Build & Release Plan
REL - Deployment/Installation
Configuration Management
CON - Configuration Management Plan
Configuration Audit
Close Phase Activities
CLO - Complete Project Closure
R
A
C
I
Role
Project Deliverable (or Activity)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.

## Sheet2
| Project Sponsor | Project Director | Project Manager | Project Team | Steering Committee
Project Charter | A | A | R | C | A
Communication Management Plan | A | C | R | I | C
Business Requirements | A | I | R | C | I
Status Reports | I | I | R | C | I