## RACI Matrix
RACI Matrix | Noida Authority-Property Management System
| Customer | Management | Program Manager | Crown | Project Manager Digitization & Analytics | Project Manager Application Development | Business Analyst | Database Adminstrator | Technical Architect | Lead Developer | Test Manager | QA Lead | Infrastructure | Configuration Manager
Initiate Phase Activities
INI - Kick Off |  | A | R |  |  | C | I |  | I | I | I | C | I | I
INI -Requirement Gathering |  | I | C |  |  | R | I | I | I | I | R | C | I | I
INI - Requirement Signoff |  | I | A |  |  | R | I | I | I | I | I | I | I | I
Project Management
Project Monitoring & Control |  | I | A |  |  | R | I | I | I | I | I |  | I | I
Risk Management |  | I | A |  |  | R | I | I | I | I | I |  | I | I
Dizitization &Scanning |  | I | I | R | A |  | I | I | I
Data Entry |  | I | I | R | A |  | I | I | I
Weekly Project Review & Status Report
Plan Phase Activities
REQ - SRS Prepare |  | I | C |  |  | C | R |  | C | I | I |  | I | I
REQ - SRS Review |  | I | R |  |  | A | C |  | C | I | I |  | I | I
REQ - SRS Approve | R | A | I |  |  | I | I |  | I | I | I |  | I | I
Design Phase Activities
DES - Design Prepare |  | I | C |  |  | A | C |  | R | I | I |  | I | I
DES - Design Review |  | I | C |  |  | R | C |  | R | I | I |  | I | I
DES - Design Approve |  | I | A |  |  | C | C |  | R | I | I |  | I | I
Database Design (Structure) | I | I | C |  | A |  |  | R
Coding Phase Activities
COD - Coding |  | I | I |  |  | A | I |  | C | R
COD - Code Review | [5 empty] | A |  |  |  | R | I
COD - Unit Testing | [5 empty] | A |  |  |  | R
Testing Phase Activities
Quality Magament Plan | [5 empty] | I | I |  | I | I | A
Product Quality | [5 empty] | A |  |  |  | R | I
Process Quality | [5 empty] | A |  |  |  |  | R
Product Audit
Process Audit
Release Phase Activities
Build & Release Plan | [5 empty] | A |  |  |  |  | R
REL - Deployment/Installation | [5 empty] | A |  |  |  | R
Configuration Management
CON - Configuration Management Plan | [5 empty] | A | [7 empty] | R
Configuration Audit
Close Phase Activities
CLO - Complete Project Closure | I | A | A |  |  | R
Scanning & Digitization
INI - Kick Off
INI - Prepare Contract
INI - Approve Contract
Project Management
Digitize all the hard copies of the documents
Setting up the scanning centre in Noida premises for A4/Legal papers and for A0/A1 drawings
collect the hard copies of the documents from the Authority’s relevant department
Scanning of the collected documents (200 Dpi or higher)
Indexing of documents linked to property ID
Storage of scanned documents
Enable Retrieval of scanned documents linked with property ID
Validate and verify consolidated data relating to all properties and capture relevant data from physical files that is missing from current web builder database
Returning of the hard copy documents back to Authority’s relevant department with acknowledgement
Carry out check on 100% of properties in each type to validate and verify data between the physical file and the web builder database
In case if data related to a property is completely missing, i.e. no file is created in the webbuilder database related to the property, then file needs to be created and data updated as per the details of the property in the Physical file
In case any information is missing, the same needs to be updated in the database
In case of any deviation in information between physical file and web builder database, then co-ordinate with the Nodal officer of the relevant department and update correct data in database after fulfilling relevant procedure set up by the Authority
Project Monitoring & Control
Risk Management
Dizitization &Scanning
Data Entry
Weekly Project Review & Status Report
Configuration Management
CON - Configuration Management Plan
Configuration Audit
Close Phase Activities
CLO - Complete Project Closure
Data Entry
Any creation, updation /change of data in the web builder database shall be done only after approval of the Nodal Officer appointed for the relevant department.
For any Chnages/ updation of Data, follow relevant procedure set up by Authority and take permissions before making any changes in the web builder.
Web based module for entering/ maintaining (approximately 96 thousand) properties
R
A
C
I
Role
Project Deliverable (or Activity)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.

## Sheet2
| Project Sponsor | Project Director | Project Manager | Project Team | Steering Committee
Project Charter | A | A | R | C | A
Communication Management Plan | A | C | R | I | C
Business Requirements | A | I | R | C | I
Status Reports | I | I | R | C | I