## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
| NOIDA PMIS Project Status Report as of 10th June,2016 | [6 empty] | Date: | 2016-06-13
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Housing: 16,999 files have been scanned with 7,96,798 pages Industrial: 7,642 files have been scanned with 15,89,728 pages Commercial: 5,450 files have been scanned with 11,01,124 pages and scanning at Commercial is completed. Residential: 505 files have been scanned with 36,347 pages Institutional:1,127 files have been scanned with 62,795 pages and no more files are there. Total :31,218 files have been scanned with 35,50,445 pages PMIS-I Application development completed and deployed and all live property integrated data can be seen by Noida Officers.However exisiting data to be validated.Also, Citizen charter data is not integrated.We developed an additional graph/report for RTI but awaiting data. Place holder and technical implementation for Citizen Charter is available. It can be enabled whenever Citizen charter APIs' are available. PMIS-II: Requirement Development: Requirement document for PMIS-II is completed and submitted to departments for review and sign off.Few changes recommended by Industrial department & housing departments in the document have been incorporated & will be resubmitted on 20th June.Commercial & Institutional depts have given sign off. Design: High level design document was submitted to NOIDA.Low level design is incremental and already in process. Development: User management and Master data is completed. Allottment process & Application for Properties getting completed by 17th June.Lease deed execution,payment schedule creation & mutation process development will get completed by 1st July.
`
Open Risks |  |  |  |  | Open Issues
Risk | Impact | Status | Date | OWNER | Issue | Impact | Status | Date | Owner
Requirments Document still not reviewed by Residential & Group Housing Departments | 1. Delay in sign off will result in delayed delivery. 2. If req doc is not signed off , then further development process will get delayed. 3. Resources deployed on the project will be sitting idle which in turn will impact commercially. | Open | 2016-05-01 | NOIDA | Citizen Charter Data Not Yet Provided | High | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes because delay in requirement sign off will significantly impact timeline of delivery.
Program Risk:
Normal
Some Risk
High Risk
Status Trend:
Improving
Steady
Deteriorating