## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
| NOIDA PMIS Project Status Report as of 20th May,2016 | [6 empty] | Date: | 2016-05-23
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Housing: 15,000 files have been scanned. Industrial: 6,500 files have been scanned Commercial: 5,450 files have been scanned and scanning at Commercial is completed. Institutional:1,127 files have been scanned and no more files are there. PMIS-I Application development completed and ready for deployment.All available required data integrated and is on line. However, Citizen charter data is not integrated yet because of non-availability. PMIS-II: Requirement Development: Requirement for PMIS-II is completed and submitted to departments for review and sign off Design: High level design document was submitted to NOIDA Development: Development of User management and Master data is completed. Working on alottment process
`
Open Risks |  |  |  |  | Open Issues
Risk | Impact | Status | Date | OWNER | Issue | Impact | Status | Date | Owner
Requirments Document still not signed by Noida Authority. | 1. Delay in sign off will result in delayed delivery. 2. If req is not being signed by 25th May, then further development process will not happen. 3. Resources deployed on the project will be sitting idle which in turn will impact commercially. | Open | 2016-05-01 | NOIDA | Citizen Charter Data Not Yet Provided | High | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes because delay in requirement sign off will significantly impact timeline of delivery.
Program Risk:
Normal
Some Risk
High Risk
Status Trend:
Improving
Steady
Deteriorating