## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
| Project Status Report 5 May-20 May | [6 empty] | Date: | 2016-05-23
| On plan |  | Issues with plan |  | At Risk |  | No Status
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Housing: 15,000 files has been scanned. Industrial: 6,500 files has been scanned Commercial: 5,450 files scanned and scanning at Commercial is completed. Institutional:1,127 file has been scanned and no more files are there. PMIS-I Application development completed ready for deployment. However, Citizen charter data is not integrated. PMIS-II: Requirement Development: Requirement for PMIS-II is completed and submitted to departments for review and sign off Design: High level design document was submitted to NOIDA Development: Development of User management and Master data is completed. Working on alottment process
Milestone Hit/Progress |  |  |  |  | Next Period Milestones
Work Item | Assigned To | Status |  |  | Milestones | Resource |  | Plan Date | Actual Date
Low level system design for Alottment process | Akshay Kumar Das | Completed |  |  | Application and alottment | Mankaran Singh, Shatrughna |  | 2016-05-30 | 2016-05-23
User Management Development | Mankaran,Ambrish,Shatrughna ,Naresh,Ajay Partap | Completed |  |  | Auto generation of alottment letter | Ambrish Verma/ Naresh |  | 2016-05-30 | 2016-05-23
User Management Testing | Dhananjay Kaushik | Completed |  |  | Alottment money payment processing | Ajay Pratap Solanki |  | 2016-04-20 | 2016-05-23
Master Data | Mankaran,Ambrish,Shatrughna ,Naresh,Ajay Partap | Completed |  |  | low level design for Possession, lease deed execution | Akshay Kumar Das |  | 2016-05-27 | 2016-05-25
Requirment Singed Off | Vishal Shukla | In Progress |  |  | Data modeling for Possession and lease deed execution | Vishal Shukla/Ankit Jain |  | 2016-05-27 | 2016-05-20
`
Open Risk |  |  |  |  | Open Issues
Issues | Impact | Status | Date | OWNER | Comments | Impact | Status | Date | Owner
Requirment still not singned by of Noida Authority. | 1. Delay in sign off will result in delayed delivery. 2. If req is not being signed by 25th May, then further development process will not happen. 3. Resources deployed on the project will be sitting idle which in turn will impact commercially. | Open | 2016-05-01 | NOIDA | Citizen Charter Data | High | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes because delay in requirement sign off will significantly impact timeline of delivery.
Track Status:
G
I
R
N
Program Risk:
Normal
Some Risk
High Risk
Status Trend:
Improving
Steady
Deteriorating