## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
|  | PROGRESS STATUS REPORT |  |  |  |  | Date: | 2016-08-16
Project Risk | Normal | Moderate | High
Status Trend | Improving | Steady | Deteriorating
Track Status | On Plan | Off Track | Deviated
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Almost 37,500 property files consist of 5 million pages are completed. Scanning of commercial and institutional properties files are completed. Industrial property files are near to completion. Process of filing in Residential department is pretty slow and it has slowed down the pace of scanning A predefined set of files or all documents in a file should be scanned. Identifying different set of documents from each file is a very slow activity and sometimes relevant official’s availability has also become a bottleneck. PMIS-1: Since, NOIDA has decided to deploy solution in Cloud, NST will procure, deploy the Document Management solution and PMIS-I in cloud. Initial hosting infrastructure procurement for PMIS-1 and DMS will be considered as a change. Expected deployment date for DMS is 24th August. NST shall commence data correction activity by 1st Sep. Cloud hosting scope shall include two Dual core CPU, 4 GB RAM, 200 GB HDD, Window 2012 server. Additional storage of 5 TB required for document storage and should be procured along with the server. NST will provide a comparison of top cloud hosting infrastructure before making any decision. This comparison will be submitted to NOIDA by 19th Aug. PMIS-II: Sprint 5 development which includes Transfer process, Mortgage, rent permission, Functional, completion Due Payment Calculation in progress and Building Plan details, Refund approval & Payment Transfer process is pending. Subsequently, next sprint consists of all backlogs from previous sprints and remaining processes of Property management. It also includes the development of final user interface approved (quite a few interfaces still require approval) by NOIDA.
Milestone Hit/Progress |  |  |  | Next Period Milestones
Work Item | Assigned To | Status |  | Milestones | Resource |  | Plan Date
Transfer Process of a property | Mankaran Singh Kohli | In Progress |  | CIC | TBD |  | 2016-08-23
Mortgage Permission of Property | Ambrish Verma | In Progress |  | Cancelation Property | TBD |  | 2016-08-23
Rent Permission | Shatrughn Kumar | In Progress |  | Split Property | TBD |  | 2016-08-23
Functional Letter | Anuj Kumar | In Progress |  | Personalized lager of allottees | TBD |  | 2016-08-23
Completion Process | Naresh Kumar | In Progress |  | Create draw slip | TBD |  | 2016-08-23
Reconciliation-Half yearly, Yearly and monthly | Ankit | In Progress |  | Gather Interview details/Noting for Industrial/Institutional/Commercial properties | TBD |  | 2016-08-23
Due Payment Calculation Engine | Ankit | Completed |  | View Notice history and notices | TBD |  | 2016-08-23
Building plan details | TBD | Pending |  | Integration API with Payment & receipt system | TBD |  | 2016-08-23
Refund approval & Payment Transfer process | TBD | Pending |  | Ui design and implementation for PMS-II | TBD |  | 2016-08-23
|  |  |  | DMS Deployment with customized feature | TBD |  | 2016-08-25
|  |  |  | Commence Data Correction Activity | TBD |  | 2016-09-01
`
Open Risk |  |  |  | Open Issues
Issues | Impact | Status | Date | Comments | Impact | Status | Date | Owner
Housing Department sign off is pending | Low | Open | 2016-07-08 | Citizen Charter Data | Low | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes, Process of scanning in residential is really cumbersome. File handling process and support is really a concern and may take ages to finish the residential department. It is recommended that all documents of Residential should be scanned.This will help hasten the process of scanning . An executive decision is required to smoothen the filing and scanning process.