## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
|  | PROGRESS STATUS REPORT AS OF 22nd JULY,2016 |  |  |  |  | Date: | 2016-07-25
Project Risk | Normal | Moderate | High
Status Trend | Improving | Steady | Deteriorating
Track Status | On Plan | Off Track | Deviated
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: 35,399 property files are completed with scanning of a total of 45,83,236 pages.Scanning of commercial and institutional properties files are completed. Industrial property files are near to completion. Residential and Group housing progress is very slow. Group housing department had space crunch &only now the space has been provided. Process of filing in Residential department is pretty slow and it has slowed down the pace of scanning we had in other departments. A predefined set of files or all documents in a file should be scanned. Identifying different set of documents from each file is very slow activity and sometimes relevant officials availability has also become a bottleneck. PMIS-I Application development completed and deployed in the noida server with available data integrated . However, Citizen charter data is not integrated because of non-availability . Data Entry activities will be started during the 1st Week of August. PMIS-II: Sprint 4 development which includes Lease Deed, Mutation, Possession etc is completed. System testing and defect fixing is in progress. Web service development for DMS is completed . NSTs' Business Analyst will work with NOIDA official during week starting from 24th July and get an agreement about user interface design.
Milestone Hit/Progress |  |  |  | Next Period Milestones
Work Item | Assigned To | Status |  | Milestones | Resource |  | Plan Date | Actual Date
Payment Engine | Ajay Partap | Completed |  | Transfer Process of a property | Dhananjay Kumar |  | 29-07-2016
Add Mutation/Substitution | Mankaran Singh Kohli | Completed |  | Mortgage Permission of Property | Dhananjay Kumar |  | 2016-08-05
Possession Order process | Ajay Partap | Completed |  | Rent Permission | Dhananjay Kumar |  | 2016-08-05
Generate Possession letter | Ajay Partap | Completed |  | Functional Letter | Dhananjay Kumar |  | 2016-08-05
Allottee Details view | Shatrughana | Completed |  | Building plan Approval | Dhananjay Kumar |  | 2016-08-05
Payment Schedule History view | Ambrish Verma | Completed |  | Completion Process | Dhananjay Kumar |  | 2016-08-05
Auto Schedule View (Land Development) | Shatrughana | Completed |  | Refund approval & Payment Transfer process | Dhananjay Kumar |  | 29-07-2016
Test Cases | Dhanajaya Kaushik | In Progress |  | Reconciliation-Half yearly, Yearly and monthly | Dhananjay Kumar |  | 29-07-2016
Bug Fixing | All Team | In Progress |  | Due Payment Calculation Engine | Dhananjay Kumar |  | 29-07-2016
`
Open Risk |  |  |  | Open Issues
Issues | Impact | Status | Date | Comments | Impact | Status | Date | Owner
Residential and housing requirements document sign off is still pending | Low | Open | 2016-07-08 | Citizen Charter Data | High | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes, Process of scanning in residential is really cumbersome. File handling process and support is really a concern and may take ages to finish the residential department. It is recommended that all documents of Residential should be scanned.This will help hasten the process of scanning . An executive decision is required to smoothen the filing and scanning process.
Option Button 48
Option Button 48