## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
| Project Status Report | [5 empty] | Date: | 2016-07-08
| On plan |  | Issues with plan | At Risk |  | No Status
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Residential, Housing and Industrial departments’ document scanning is in progress. We are waiting for a letter from NOIDA to start scanning of Account departments’ files. We have been advised to do the scanning of Land records as well. Once we get the letter, we will plan for that. PMIS-II * Requirement for Group Housing, Commercial, Institutional has been signed off. We will get sign off from Residential department early next week. * Sprint IV is in progress and planned to be finished by 18th July. Sprint IV includes lease deed, mutation, common component like letter generation, Payment calculation engine etc. * Logical separation of code was required in certain cases and that is completed. * Another parallel sprint is also in progress which includes management of few master data elements, changes in allocation process etc. * In current sprint, an interface with accounting system was created and tested. * Another set of interface required for document management system integration is finished and will be delivered to DAMCQ by 11th July.
Milestone Hit/Progress |  |  |  | Next Period Milestones
Work Item | Assigned To | Status |  | Milestones | Resource |  | Plan Date | Actual Date
Webservice - Post financial information account | Preeetam Singh | Completed |  | Payment Engine | Ajay Partap |  | 2016-07-07
Webservice - Retrieve financial information from accounts | Preeetam Singh | Completed |  | Add Mutation/Substitution | Mankaran Singh Kohli |  | 2016-07-11
Auditing Engine | Ambrish Verma | Completed |  | Possession Order generation | Mankaran Singh Kohli |  | 2016-07-13
Lease deed + Checklist - Letter just after allotment is done | Mankaran Singh Kohli | Completed |  | Generate Possession letter | Mankaran Singh Kohli |  | 2016-07-14
View & Update Property (Tabbing) | Ambrish Verma | Completed |  | Allottee Details view | Shartughana |  | 2016-07-11
Business Rule Engine,Rules based Process of departments Allotment Rules,Lease deed Rules,Possession Rules | Ajay Partap Shatrughana | In process (Completead today) |  | Payment Schedule History view | Ambrish Verma |  | 2016-07-13
Add Lease deed details | Mankaran Singh Kohli | In process (Completead today) |  | Auto Schedule View (Land Development) | Shartughana |  | 2016-07-13
Property Details,Subsitution,Transfer | Ambrish Verma | In process |  | Test Cases for Sprint-IV | Dhanajaya Kaushik |  | 2016-07-11
Database | Ankit | Completed |  | Testing | Dhanajaya Kaushik |  | 2016-07-14
User Stories | Gaurav/Ankit/Arun | Completed
`
Open Risk |  |  |  | Open Issues
Issues | Impact | Status | Date | Comments | Impact | Status | Date | Owner
Residential,Industrial And housing requirment sign off pending | High | open | 2016-06-14 | Citizen Charter Data | High |  | 2016-03-26 | NOIDA
Change
Payment gateway of IndusInd bank need to be integrated with Rel-1 deliverable. Dhananjay is coordinating with Bank. Hopefully, he will have detailed meeting with Bank where he will define action points which may require action from NOIDA.
Executive Decision Required(Y/N): Yes because delay in requirement sign off will significantly impact timeline of delivery.
Track Status:
G
I
R
N
Program Risk:
Normal
Some Risk
High Risk
Status Trend:
Improving
Steady
Deteriorating