## IFF Intranet (hidden)
| Project Dashboard(IFF Intranet-2) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## StoneyBrooks (hidden)
| Project Dashboard(Procurement System) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## HereMatch (hidden)
| Project Dashboard(HereMatch) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## EER (hidden)
| Project Dashboard(EER) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## SonicWall (hidden)
| Project Dashboard(SonicWall) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Artcore (hidden)
| Project Dashboard(Artcore) | [6 empty] | 2012-08-24
Program Risk: | Normal | Some Risk | High Risk
Status Trend: | Improving | Steady | Deteriorating
Track Status: | On plan | G | Issues w/ plan | Y | At Risk | R | No Status | N
Project Status
Y
G
Key Messages:
Milestone Hit/Progress |  |  |  |  | Milestone Missed
Module | Elementary Description |  |  |  | Project | Task |  | Resource | New Date
Next Week Task |  |  |  |  | Open Issues
Module | Brief Description of next week task |  |  |  | Issues | Impact | Status | Date | Owner
Key Changes |  |  |  |  | Open Risk
Change |  | Project | Agreed |  | Risk | Probability | Impact | Status | Owner
Executive Actions/Decisions Needed :

## Noida Project PMIS
| Project Status Report Sprint 3 | [6 empty] | Date: | 2016-06-24
| On plan |  | Issues with plan |  | At Risk |  | No Status
Project Status
Project | Indicator | Key Message
PMIS | I | Digitization: Housing: 15,000 files has been scanned. Industrial: 6,500 files has been scanned Commercial: 5,450 files scanned and scanning at Commercial is completed. Institutional:1,127 file has been scanned and no more files are there. Residential :1000 file hase been scanned PMIS-I Application development completed ready for deployment. However, Citizen charter data is not integrated. PMIS-II: Requirement Development: Requirement for PMIS-II is completed and submitted to departments for review and sign off Design: High level design document was submitted to NOIDA Development: Group Housing,Commercial,Institutional sign off comleted. Development of User management , Master data is completed and alottment process is completed. Rent Permission Mortgage,Lease Deed,Functional,Possession,Completion
Milestone Hit/Progress |  |  |  |  | Next Period Milestones
Work Item | Assigned To | Status |  |  | Milestones | Resource |  | Plan Date | Actual Date
Bulk Upload | Shartughana | Completed |  |  | Lease Deed execution | Ajay Partap |  | 2016-06-27
Allotment | Ambrish | Completed |  |  | Possession | Mankaran Singh, |  | 2016-06-27
Refund Money | Mankaran | Completed |  |  | Mortgage | Naresh |  | 2016-06-27
Approved of request ,Application Form | Naresh | Completed |  |  | low level design for Functional rent permission,completion,lease deed,mortage | Akshay Kumar Das |  | 2016-05-27
Manage Allote List | Anuj | Completed |  |  | Data modeling Functional rent permission,completion,lease deed,mortage | Vishal Shukla/Ankit Jain |  | 2016-06-27
Databse Cerateion | Ankit | Completed |  |  | Functional | Ambrish |  | 2016-06-27
Testing | Dhanjay Kaushik | in process |  |  | Completion | Anuj |  | 2016-06-27
[5 empty] | Rent Permission | Shartughana |  | 2016-06-27
`
Open Risk |  |  |  |  | Open Issues
Issues | Impact | Status | Date | OWNER | Comments | Impact | Status | Date | Owner
[5 empty] | Citizen Charter Data | High | Open | 2016-03-26 | NOIDA
Executive Decision Required(Y/N): Yes because delay in requirement sign off will significantly impact timeline of delivery.
Track Status:
G
I
R
N
Program Risk:
Normal
Some Risk
High Risk
Status Trend:
Improving
Steady
Deteriorating