## Instruction
|  | NST Asset Risk Register Sheet |  |  |  | Last Update on
Guidelines for using the Asset Risk Register Sheet
Risk analysis is an evaluation of the identified risk events to determine the likelihood of the events occurring and their impact, to assign a risk rating based on the project criteria and to prioritize the risks.
For each risk event, the following risk analysis guidelines can be used:
| Probability |  |  |  | Vulnerability (Impact)value
| For each risk identified the likelihood that the event will occur. The likelihood of occurrence can be categorized as: |  |  |  | The vulnerability of each risk are attributed to a characterization value as follows:
| Rating | Description | Score |  | Rating | Description | Score
| Near certainty | Event that has a greater than 75% chance of occurring | 5 |  | Showstopper | The effect is catastrophic; the organization may face significant loss and impact. The project will fail. | 4
| Highly likely | Event that has between a 51 – 75% chance of occurring | 4 |  | Critical | The impact is serious and the project may be largely affected due to the risk. There could be huge delays and the project could be postponed due to it. | 3
| Likely | Event that has between a 20 – 50% chance of occurring | 3 |  | Marginal | The risks could affect in small delays in schedule . | 2
| Unlikely | Event that has between a 10 – 20% chance of occurring | 2 |  | Negligible | The impact of these risks on the project could be minimal. | 1
| Remote | Event that has a 0 – 10% chance of occurring | 1
After the probability and impact for the risks have been assigned, the risk level\value needs to be determined. A risk can be categorized based on the risk level which is a product of the numeric values of Probability and Impact. The higher the risk level the higher its priority. For Asset the risk level is calculated as per the table given below:
Risk Value = (probability of event) + ( Vulnerability) +(CIA Value)
|  | Probability (P) Levels |  | Vulnerability (V) Values | CIA Value (C) | Risk Values (P+I+C)
|  | 1 - (R)emote |  | 1 - (N)egligible | 1- Low | 3 to 5 - Normal/Trivial
|  | 2 - (U)nlikely |  | 2 - (M)arginal | 2- Medium | 6 to 7 - Low
|  | 3 - (L)ikely |  | 3 - (C)ritical | 3- High | 8 to 10 - Medium
|  | 4 - (H)ighly likely |  | 4 - (S)howstopper |  | 11 to 12 - High
5 - (N)ear certainty
Risk Level Value definition
3 to 5: No action required
6 to 7: To be reviewed regularly and Organization will accept risk up to this level
8 to 10: Medium level risk, mitigation to be planned in a period of six months. But in case of project, period may be vary on the basis of project duration
11 to 12: High Level risk, Mitigation immediately required
Version History:
S.No | Version No | Prepared By | Date | Approved By
1 | 1 | Abhishek | 2009-10-03 | Sudhir Sexana
2 | 1.1 | Abhishek | 2011-02-12 | Sudhir Sexana
3 | 2 | Rahul | 2012-10-27 | Dhananjay Kr.
4 | 2.1 | Rahul | 2015-07-29 | Dhananjay Kr.

## Risk Register
Project / Engagement / Function Name: |  |  |  | Property Management Information System (PMIS) | [11 empty] | Last updated on : | 2016-01-07
Responsible Person for tracking and addressing the risk: |  |  |  | PM
Risk ID | Risk Identification Date | Risks | Risk related to | Probability | Impact | Asset Value |  |  |  | Risk Value | Risk Handling Approach | Mitigation Plan | Assigned To | Business Process | Action Date(MM/DD/YYYY) | Action Taken | Status
[6 empty] | C | I | A | Final
1 | 2016-01-12 | The authenticity of the record cannot be ascertained from the converted record | Digitization | 3 | 3 | 3 | 3 | 3 | 3 | 9 | Mitigate to be Planned | Processes and metadata standards should be implemented as outlined in the Management Plan for the Converted Records | Vishal Shukla | Software Development Process
2 | 2016-01-12 | A full and accurate record may not result from the digitising process, e.g. pages missing | Digitization | 3 | 3 | 2 | 2 | 2 | 2 | 8 | Mitigate to be Planned | maintain a log book for Incoming and out going files from the Record Room department and get it signed by the record room incharge. Maintained record of scanned pages in the file in excel format |  | Software Development Process
4 | 2016-01-12 | Converted records may be large in file size causing a slow response time to view from the desktop | Digitization | 3 | 2 | 1 | 2 | 2 | 2 | 7 | Accept |  |  | Software Development Process |  | Large source records may be split to facilitate smaller electronic records being created, as per the Digitisation Processing Plan. Software and hardware may need to be upgraded and additional memory purchased.
5 | 2016-01-20 | Security of converted records may be compromised due to the ease with which electronic documents are copied and disseminated | Digitization | 3 | 1 | 1 | 2 | 2 | 2 | 6 | Accept | Processes and security controls should be implemented as outlined in the Management Plan for the Converted Records |  | Software Development Process
6 | 2016-01-20 | Converted records may be lost due to hardware failure or disaster | Digitization | 2 | 1 | 1 | 2 | 2 | 2 | 5 | Avoid | Backup and restore processes outlined in the Management Plan for the Converted Records |  | Software Development Process
7 | 2016-01-20 | Organisational resistance to acceptance of digitised information as a official record | Digitization | 3 | 1 | 1 | 2 | 2 | 2 | 6 | Accept | Education, promotion & training. Active endorsement from Management |  | Software Development Process
8 | 2016-01-04 | Poor capture of full User requirements. Failure to meet minimum requirements.Failure to achieve business benefits. Need to rework solution after rollout.Failed delivery | Application Development | 2 | 3 | 3 | 2 | 2 | 3 | 8 | Mitigate to be Planned | Focus on capturing user specific Requirements at the begining of project. Involve experienced BA with good dececision making ability and delivery commitment on time. Accountable process owners. |  | Software Development Process | 2016-01-12 | Hired Experienced BA for this project Make Accountable in RACI Matrix | Inactive
9 | 2016-01-20 | Lack of Academic and Departmental buy-in Failure to achieve business benefits. Ineffective work practices. More fragmented processes. Poor Communication. | Application Development | 2 | 3 | 3 | 2 | 2 | 3 | 8 | Mitigate to be Planned | Ensure User Requirements are properly assessed. Invlove Subject matter expert into Requirment Gathering. Communications and planning focus. Appoint Project Manager for client communication. |  | Software Development Process
10 | 2016-01-20 | Poor business processes A system based on over-complicated, badly engineered business processes will itself be over-complicated and badly engineered | Application Development | 2 | 1 | 3 | 2 | 2 | 3 | 6 | Accept | Revised business processes before constructing user spec. |  | Software Development Process
11 | 2016-01-20 | Few resources are planned for other projects also. So backup plan is needed in case any resource get shifted to other project | Application Development | 2 | 2 | 1 | 1 | 3 | 3 | 7 | Accept |  |  | Software Development Process | 2016-02-01 | Back up plan has been definedin PMP | Inactive

## ListVal (2)
Category | Risk Categories (or RBS) | Status | Strategy | Description
Scope Volatility | Software Development Process |  | Avoid | Actions to ensure threat cannot occur by avoiding the project/scenario
Schedule | Quality Process |  | Transfer | Transfer to third party
Cost |  |  | Mitigate | Actions that will decrease probability/impact
HR |  |  | Accept (Actively) | Take no strategic actions except building contingency reserve of time, money, resource
Performance |  |  | Accept (Passively) | Take no strategic actions
Info security
Business Continuity
|  |  | Residual Risks | Risks that remain after planned responses have been taken, including accepted risks