## Sheet2 (hidden)
ID | bug_id | component | Release/Module | short_desc | RCA | RCA Description | assigned_to | bug_severity | priority | bug_status | resolution | opendate | changeddate
467 | 7812 | ES | CR | Delete Machine : All Check-box |  |  | ksahoo@svam.com | major | P3 | CLOSED | FIXED | 2016-03-15 01:40 | 2016-03-16 01:41
441 | 7810 | ES | CR | Delete Machine : All the machine having status Unassigned |  |  | ksahoo@svam.com | major | P2 | CLOSED | FIXED | 2016-03-15 01:27 | 2016-03-16 01:40
422 | 7811 | ES | CR | Delete Machine : delete button |  |  | ksahoo@svam.com | major | P1 | CLOSED | FIXED | 2016-03-15 01:34 | 2016-03-16 01:59
281 | 6874 | ES | CR | Activate Manufacturer |  |  | ksahoo@svam.com | major | P2 | VERIFIED | CLOSED | 2015-06-19 04:41 | 2015-06-19 09:17
280 | 6873 | ES | CR | Deactivate Manufacturer |  |  | ksahoo@svam.com | major | P2 | VERIFIED | CLOSED | 2015-06-19 04:39 | 2015-06-19 09:07
172 | 7915 | ES | CR | MANAGE MEMBERSHIP CONFIGURATIONS : void days |  |  | ksahoo@svam.com | normal | P3 | RESOLVED | FIXED | 2016-04-22 08:44 | 2016-05-04 05:39
171 | 7911 | ES | CR | manage membership : Last revive used date: update |  |  | ksahoo@svam.com | normal | P3 | RESOLVED | FIXED | 2016-04-22 07:22 | 2016-04-25 02:28
105 | 6876 | ES | CR | Create/update manufacturer : runtime error |  |  | ksahoo@svam.com | normal | P4 | REOPENED | --- | 2015-06-19 04:57 | 2015-07-28 07:03
102 | 7725 | ES | CR | CR: Sub Agent & Subsidiary ID duplicate on drop-down selection change |  |  | ksahoo@svam.com | normal | P3 | REOPENED | --- | 2016-02-16 03:55 | 2016-03-04 04:26
97 | 7877 | ES | CR | Delete Machines : not showing the machine on Delete Machines page |  |  | ksahoo@svam.com | major | P1 | REOPENED | --- | 2016-04-05 07:50 | 2016-04-28 00:57
84 | 7743 | ES | CR | CR : Assigned machine should not displayed in unassigned machine drop-down under map machine & replace machine |  |  | Amit.Kumar@svam.com | major | P2 | ASSIGNED | --- | 2016-02-17 08:21 | 2016-03-03 09:07
79 | 7824 | ES | CR | Delete Machine : Grid Checkbox All |  |  | ksahoo@svam.com | major | P4 | NEW | --- | 2016-03-16 02:09 | 2016-03-16 02:09
56 | 7756 | ES | CR | CR: Customer admin can create Subsidiaries, SubAgents & Locations for his customer only |  |  | ksahoo@svam.com | major | P2 | NEW | --- | 2016-02-19 07:44 | 2016-02-19 07:44
19 | 7891 | ES | CR | DELETE MACHINES : showing only Unassigned machine |  |  | ksahoo@svam.com | major | P1 | NEW | --- | 2016-04-07 01:44 | 2016-04-22 09:08
18 | 7829 | ES | CR | Import machine Shipping |  |  | ksahoo@svam.com | major | P1 | NEW | --- | 2016-03-18 03:49 | 2016-03-18 04:13

## RCA Analysis
Count of short_desc | Column Labels
Row Labels | Code | Enhancement | Grand Total
Sprint1 | 30 | 5 | 35
Coding Error | 1 |  | 1
Design Error | 1 |  | 1
Logic Error | 2 |  | 2
Minor Change |  | 3 | 3
Missing Function | 1 |  | 1
Partial Implemented | 6 |  | 6
Requirement Missing |  | 2 | 2
Requirement Not Implemented | 17 |  | 17
Specification Error | 1 |  | 1
Text Message | 1 |  | 1
Sprint2 | 31 | 4 | 35
Coding Error | 3 |  | 3
Minor Change |  | 2 | 2
Partial Implemented | 1 |  | 1
Requirement Missing |  | 1 | 1
Requirement Not Implemented | 26 | 1 | 27
Unknown | 1 |  | 1
Sprint3 | 36 | 2 | 38
Coding Error | 1 |  | 1
Design Error | 2 |  | 2
Partial Implemented | 3 |  | 3
Requirement Missing |  | 2 | 2
Requirement Not Implemented | 29 |  | 29
Specification Error | 1 |  | 1
Sprint4 | 27 | 2 | 29
Coding Error | 1 |  | 1
Minor Change |  | 1 | 1
Requirement Missing |  | 1 | 1
Requirement Not Implemented | 26 |  | 26
Sprint5 | 29 | 1 | 30
Coding Error | 1 |  | 1
Design Error | 3 |  | 3
Minor Change |  | 1 | 1
Requirement Not Implemented | 21 |  | 21
Specification Error | 4 |  | 4
Grand Total | 153 | 14 | 167

## Noida_BugList
ID | bug_id | component | Release/Module | short_desc | RCA | RCA Description | assigned_to | bug_severity | priority | bug_status | resolution | Created Date | Resolved Date | Closed Date
1 | 1 | User Management | Sprint1 | Login Page - 'UserName' should be like Username throughout the application. | Design | UI Design Issue | Dhananjay Kaushik | 4 - Low | 2 | Closed | --- | 30/05/2016 15:05:37 | 2016-01-06 15:47 | 2016-06-06 15:32
2 | 2 | Authentication & Authorization | Sprint1 | User should never get navigated to the home page once he/she has logged out . | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 30/05/2016 15:15:25 | 2016-01-06 16:20 | 2016-06-06 15:32
3 | 3 | Authentication & Authorization | Sprint1 | User should never get navigated to the log in page once he/she clicks on change password link available in home page screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 30/05/2016 15:20:34 | 2016-01-06 13:41 | 2016-06-06 15:26
4 | 4 | Authentication & Authorization | Sprint1 | Change Password- Cancel button functionality is not working. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 30/05/2016 15:27:44 | 2016-01-06 15:48 | 2016-06-06 15:37
5 | 5 | Super Admin Role Management | Sprint1 | UM-Edit functionality is not working. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 30/05/2016 16:04:56 | 14/06/2016 18:39:52 | 14/06/2016 18:40:07
6 | 6 | Super Admin Role Management | Sprint1 | By clicking on 'Edit' tab in Edit User Role the roles are getting deleted.. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 30/05/2016 16:07:15 | 2016-01-06 15:14 | 2016-02-06 13:53
7 | 7 | Super Admin Role Management | Sprint1 | By clicking on 'role name user is getting navigated to the 'View Roles' screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 30/05/2016 16:11:51 | 14/06/2016 18:34:21 | 14/06/2016 18:36:39
8 | 8 | Authentication & Authorization | Sprint1 | Error message should be displayed in case user enters an incorrect OTP and click on OK button on ' Forgot Password' screen. | Code | Business Rule | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 30/05/2016 16:44:00 | 2016-01-06 16:19 | 2016-06-06 14:42
9 | 9 | Admin -Role Management | Sprint1 | An appropriate message should be displayed when an user do not select an 'Application' and click on Add button on 'Add User Rol'. screen. | Code | Text Message | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 30/05/2016 18:06:48 | 2016-01-06 15:32 | 2016-02-06 14:14
10 | 10 | Admin- Menu Mapping | Sprint1 | The grid is not appearing as per the user story in ' Manage User Roles' screen. | Design | UI Design Issue | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 30/05/2016 18:37:48 | 13/06/2016 16:32:21 | 17/06/2016 18:38:23
11 | 11 | Authentication & Authorization | Sprint1 | UM: User name and Password- Mandatory field should be displayed with an *(asterisk) sign. | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 31/05/2016 12:28:02 | 2016-10-06 10:54 | 17/06/2016 18:40:26
12 | 12 | Authentication & Authorization | Sprint1 | UM: User name should not be more than 15 characters. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 31/05/2016 12:42:43 | 2016-01-06 15:47 | 2016-06-06 15:32
13 | 13 | Authentication & Authorization | Sprint1 | UM: The error message should be displayed correctly in case user enter incorrect Username or Password and make other as blank. | Code | Text Message | Dhananjay Kaushik | 4 - Low | 2 | Closed |  | 31/05/2016 12:48:30 | 2016-01-06 13:43 | 2016-06-06 15:05
14 | 14 | Admin -Role Management | Sprint1 | UM: Add User Role screen : The mandatory fields should be displayed with an *(asterisk). | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 31/05/2016 14:28:04 | 2016-01-06 15:14 | 2016-02-06 14:14
15 | 15 | Authentication & Authorization | Sprint1 | UM: Forgot Password- OTP should not be generated upon entering an invalid user name also an appropriate message should be displayed. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 31/05/2016 14:44:33 | 2016-02-06 20:58 | 2016-06-06 15:24
16 | 16 | Authentication & Authorization | Sprint1 | UM: Forgot Password- OTP should not be generated upon entering an invalid user name also an appropriate message should be displayed. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 31/05/2016 15:31:49 | 2016-01-06 16:20 | 2016-06-06 15:35
17 | 17 | Authentication & Authorization | Sprint1 | UM: Forgot Password screen - ' Regenerate OTP ' is not working. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 31/05/2016 17:09:47 | 23/06/2016 14:28:31 | 28/06/2016 12:16:20
18 | 18 | Authentication & Authorization | Sprint1 | UM: Copy / Paste functionality should not work for entering any password/user name. | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 31/05/2016 18:11:05 | 2016-01-06 16:31 | 2016-06-06 14:56
19 | 19 | Authentication & Authorization | Sprint1 | UM: Super admin- change password screen: Old Password, New Password and Confirm New Password should not be the same. | Code | Business Rule | Dhananjay Kaushik | 2 - High | 1 | Closed |  | 31/05/2016 18:26:33 | 2016-01-06 16:19 | 2016-06-06 15:06
20 | 20 | Authentication & Authorization | Sprint1 | UM: Super admin- Change password screen: New Password and Confirm New Password should not be of one characters. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 31/05/2016 18:44:01 | 2016-01-06 15:49 | 2016-06-06 12:28
21 | 21 | Super Admin Role Management | Sprint1 | UM: Super Admin- :Edit functionality is not working on ' Edit Admin Role' screen. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-01-06 12:17 | 14/06/2016 18:56:38 | 14/06/2016 19:08:07
22 | 22 | Super Admin Role Management | Sprint1 | UM- Super Admin: User should not be able to navigate to the previous screen/page when he/she logged out successfully by clicking on backspace button. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-01-06 12:54 | 2016-02-06 21:00 | 2016-06-06 14:58
23 | 23 | Property Management | Sprint2 | UM: Admin- Edit Property screen: User is unable to edit any property. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-01-06 16:51 | 2016-02-06 21:03 | 2016-06-06 14:49
24 | 24 | Property Management | Sprint2 | UM : Admin- Add Property screen : User is unable to add any property. | Code | Partial Implemented | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 2016-01-06 17:01 | 2016-10-06 10:45 | 17/06/2016 18:39:16
25 | 25 | Scheme Management | Sprint2 | MDM: User is unable to add a new scheme. | Code | Partial Implemented | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 2016-02-06 16:20 |  | 17/06/2016 14:19:06
26 | 26 | Property Management | Sprint2 | Add Property Screen : Duplicate data are displaying for department, sector and property type fields. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 2016-02-06 17:45 | 2016-02-06 21:02 | 2016-06-06 14:47
27 | 27 | Scheme Management | Sprint2 | Edit Scheme : In bank section - The duplicate entry should not be entered.. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-02-06 18:26 | 2016-08-06 18:58 | 17/06/2016 14:39:33
28 | 28 | Property Management | Sprint4 | Manage Property screen : User is unable to add a new Property. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 1 | Closed |  | 2016-02-06 18:48 | 2016-08-08 16:06 | 26/08/2016 17:19:11
29 | 29 | Scheme Management | Sprint2 | Add Scheme: The date format should be in MM/ DD /YYYY through out the application | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 3 | Closed |  | 2016-02-06 18:51 | 18/07/2016 18:03:48 | 19/07/2016 13:24:17
30 | 30 | Scheme Management | Sprint2 | Master data Management : Server Error in '/' Application. | Code | Logic Error | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 2016-02-06 18:55 | 2016-02-06 20:44 | 2016-06-06 15:26
31 | 31 | Super Admin-User Management | Sprint1 | UM: Super Admin- Unable to navigate to view user screen once click on back button on 'View User' screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-03-06 19:09 | 2016-09-06 12:14 | 2016-09-06 18:31
32 | 32 | Super Admin-User Management | Sprint2 | UM: Super Admin: The search functionality is not working for super admin and admin. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-08-06 18:00 | 19/07/2016 16:51:23 | 19/07/2016 18:52:21
33 | 33 | Scheme Management | Sprint2 | Noida Project: Regression/Suggestion: UI and spelling mistakes. | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 2016-09-06 12:50 | 22/07/2016 23:44:47 | 23/07/2016 18:27:15
34 | 34 | Scheme Management | Sprint2 | Master Data : Admin- getting "Server Error in '/' Application" while user is trying to 'Remove' any scheme on " Manage scheme" screen. | Code | Logic Error | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 2016-09-06 13:03 | 2016-09-06 18:42 | 17/06/2016 18:33:21
35 | 35 | Scheme Management | Sprint2 | Noida Authority - MDM- Admin: User is unable to edit the bank details while trying to edit an scheme. | Code | Partial Implemented | Dhananjay Kumar | 2 - High | 3 | Closed |  | 2016-09-06 13:27 | 17/06/2016 19:00:48 | 19/07/2016 13:35:35
36 | 36 | Admin- Menu Mapping | Sprint1 | UM- Super Admin: In 'User Mapping with Role' screen the Action column should have ‘Add’ (But not be visible if the user already mapped to the selected role). | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-09-06 15:25 | 14/06/2016 18:35:34 | 14/06/2016 18:37:02
37 | 37 | Super Admin-User Management | Sprint1 | UM- Super admin: Filed is missing in Add user screen - " Comments : Textbox (optional)." | Code | Partial Implemented | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 2016-09-06 15:34 | 2016-10-06 10:52 | 14/06/2016 19:09:44
38 | 38 | Super Admin-User Management | Sprint1 | UM- Super admin is unable to edit the User name on 'Edit User ' name . | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-09-06 16:23 | 14/06/2016 18:53:52 | 14/06/2016 18:54:13
39 | 39 | Super Admin-User Management | Sprint1 | UM: Super admin- Edit User screen : Field label validation for email is not working for E-mail when enter 200 characterless. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-09-06 16:59 | 2016-09-06 18:45 | 17/06/2016 16:02:28
40 | 40 | Super Admin Role Management | Sprint1 | An Admin ( PMS application ) is not able to assign more than one role to an user. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-10-06 13:32 | 2016-10-06 13:54 | 14/06/2016 19:18:38
41 | 41 | Super Admin Role Management | Sprint1 | UM-Super Admin is unable to map an admin role on " Menu Mapping for Admin Roles" screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-10-06 14:57 | 2016-10-06 18:05 | 14/06/2016 19:11:45
42 | 42 | Property Management | Sprint2 | UM/MDM-Tab button and Arrow button should work while adding a new property | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 2016-10-06 16:18 | 2016-10-06 18:08 | 17/06/2016 18:45:30
43 | 43 | Property Management | Sprint4 | MDM- Admin- Display issue on view property screen | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-10-06 16:41 | 13/06/2016 14:16:06 | 17/06/2016 19:00:55
44 | 44 | Manage Notification | Sprint4 | MDM- Admin-Display issue on Add notification and view notification. | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-10-06 18:16 | 13/06/2016 11:38:31 | 17/06/2016 18:52:14
45 | 45 | Manage Notification | Sprint4 | MDM- Admin-Server error while user try to enter more than 150 charecters as ' notification name and then save. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-10-06 18:23 | 2016-10-06 18:45 | 17/06/2016 18:49:06
46 | 46 | Admin -Role Management | Sprint2 | UM- Admin- Role name should be note more than 150 charecteres (with only space as special character) | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 13/06/2016 12:15:42 | 17/06/2016 18:59:37 | 17/06/2016 19:01:38
47 | 47 | Admin -Role Management | Sprint2 | Um- Admin should not have access to more than one application. | Code | Business Rule | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 13/06/2016 13:16:06 | 13/06/2016 16:11:28 | 14/06/2016 19:20:47
48 | 48 | Scheme Management | Sprint2 | MDM- Admin- The data from department section should not displayed once removed by clicking on remove link. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 13/06/2016 13:37:24 | 13/06/2016 13:56:51 | 17/06/2016 18:57:19
49 | 49 | Property Management | Sprint2 | MDM- Admin: Admin should not be able to add a property for ( Property/Plot No,Covered Area (Sq.Mtr) ,Floor Area Ratio ,Civil Cost,Actual Area (Sq.Mtr) and Charges (INR) =120909.00) | Code | Data Error | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 13/06/2016 15:25:31 | 14/06/2016 18:38:04 | 14/06/2016 18:38:14
50 | 50 | Scheme Management | Sprint2 | MDM- Admin: As appropriate error message should be displayed for ' Department*' and ' Sectors' on Add Property screen. | Code | Text Message | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 13/06/2016 16:10:01 | 13/06/2016 17:39:40 | 17/06/2016 18:59:35
51 | 51 | Scheme Management | Sprint2 | MDM-Admin: Admin should be able to edit 'Deduction field on edit refund screen and server error should not come. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 13/06/2016 17:18:57 | 17/06/2016 18:30:27 | 17/06/2016 18:30:34
52 | 52 | Scheme Management | Sprint4 | MDM-Submit button functionality is not working upon wrong entry in Deduction and Refund Description* | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 13/06/2016 18:11:55 | 2016-01-07 16:19 | 15/07/2016 10:43:39
53 | 53 | Scheme Management | Sprint4 | MDM- Admin is unable to add scheme with ( with Bank type as - Others) | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 17/06/2016 14:32:02 | 28/06/2016 12:30:13 | 15/07/2016 11:05:56
54 | 54 | Authentication & Authorization | Sprint1 | UM- Admin- Forgot password functionality is not working ( The new password is not working ) | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 17/06/2016 15:43:16 | 21/06/2016 14:45:32 | 21/06/2016 17:47:01
55 | 55 | Property Management | Sprint2 | MDM: Calculation mistake for 'Total Property Cost (INR)' on Add Property screen. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 17/06/2016 18:19:12 | 27/07/2016 16:09:08 | 27/07/2016 16:22:15
56 | 56 | Admin -Role Management | Sprint1 | UM-Suggestion - Admin- Message should be displayed when an admin 'x' ( who is admin for PMS) tries to map a role to another admin Y ( who is also an admin to same application PMS) | Code | Text Message | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 18/06/2016 13:16:08 | 21/06/2016 14:25:39 | 28/06/2016 12:08:40
57 | 57 | Super Admin-User Management | Sprint1 | UM: Manage Users screen-The lock button should be displayed as Unlock by clicking on 'Lock' link and the particular user should be locked/ unlocked- vice versa. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 21/06/2016 12:37:31 | 21/06/2016 13:05:12 | 21/06/2016 13:24:51
58 | 58 | Add Application Details | Sprint3 | Allotment: Add Application screen : User is unable to get the appropriate message for non mandatory fields. | Code | Text Message | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 27/06/2016 18:52:24 | 18/07/2016 18:24:12 | 18/07/2016 19:41:45
59 | 59 | Add Application Details | Sprint3 | Allotment: Unable to test anything for Allotment - Getting server error. | Code | Data Error | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 28/06/2016 12:43:35 | 28/06/2016 13:57:26 | 28/06/2016 16:04:49
60 | 60 | Add Application Details | Sprint3 | Allotment: Add application-User Should not be allowed to enter 0 as amount deposit through RTGS while adding any application. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 28/06/2016 15:14:40 | 19/07/2016 16:47:59 | 22/07/2016 19:51:36
61 | 61 | Edit Application Details | Sprint3 | Allotment-Edit Application: User should be able to edit any application successfully. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 28/06/2016 15:44:22 | 29/06/2016 18:54:47 | 15/07/2016 19:20:06
62 | 62 | View Application Details | Sprint3 | Allotment: View Application: User is not able to view the fields' value as entered for any application. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 28/06/2016 17:46:44 | 2016-02-08 15:50 | 2016-03-08 13:55
63 | 63 | Add Bulk Application Entries | Sprint3 | Allotment: Bulk Application- Unable to upload the bulk application. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 29/06/2016 20:48:13 | 18/07/2016 12:32:44 | 19/07/2016 13:26:51
64 | 64 | Scheme Management | Sprint2 | MDM- Add Scheme: Issue in the fields Installment Money,Allotment Money,Lease Rent and Floor Area Ratio | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 30/06/2016 13:47:05 | 18/07/2016 18:53:14 | 19/07/2016 13:13:11
65 | 65 | Allotment of Property | Sprint3 | Allotment: Manage Allotment- Issue in Add Allotment Details screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 1 | Closed |  | 30/06/2016 14:09:17 | 22/07/2016 23:41:14 | 23/07/2016 18:33:51
66 | 66 | Admin -Role Management | Sprint1 | UM( Regression)- Super admin- Issue in editing a role and user is unable to map a role ( blank role). | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 2016-01-07 15:52 | 2016-01-07 18:52 | 15/07/2016 10:21:49
67 | 67 | Scheme Management | Sprint2 | MDM: The edit scheme link is not working on view scheme screen. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 15/07/2016 11:25:13 | 15/07/2016 11:38:02 | 15/07/2016 18:55:46
68 | 68 | Property Management | Sprint2 | MDM: Browser specific issue-Unable to add the property properly, as the total property cost is calculating as 0.( Working in Mozilla) | Design | Compatibility Issue | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 15/07/2016 19:04:32 | 19/07/2016 11:26:48 | 19/07/2016 12:52:47
69 | 69 | Admin- Menu Mapping | Sprint1 | UM: User mapping with role screen : The new added user with role is not displaying correctly in the grid. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 18/07/2016 13:23:29 | 18/07/2016 13:51:31 | 18/07/2016 13:52:51
70 | 70 | Add Application Details | Sprint3 | Allotment: User is unable to add any application for any new scheme added. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 18/07/2016 17:54:22 | 18/07/2016 18:02:00 | 18/07/2016 18:02:04
71 | 71 | Add Application Details | Sprint3 | Allotment: Suggestion- Add application- Under payment information section only those bank should be displayed which was added during the time of adding the scheme. | Code | Business Rule | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 19/07/2016 12:03:09 | 19/07/2016 16:49:43 | 22/07/2016 19:49:20
72 | 72 | Initiate Refund for Unsuccessful Applicants | Sprint3 | Allotment: Refund-Manage refund screen : Getting server error while user click on View list under action column. | Code | Data Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 19/07/2016 12:18:28 | 19/07/2016 16:00:38 | 22/07/2016 17:53:16
73 | 73 | Approve/Reject request | Sprint3 | Allotment: User is able to approve /reject on 'Allottee List Request' again and again. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 19/07/2016 12:27:01 | 27/07/2016 13:05:24 | 2016-01-08 17:37
74 | 74 | Property Management | Sprint2 | MDM: Manage Property- User is able to select the total area out of range from ( Area range) selected. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 19/07/2016 13:04:30 | 19/07/2016 19:28:58 | 21/07/2016 17:46:52
75 | 75 | Scheme Management | Sprint4 | MDM-Edit scheme-The status of any new scheme added should not be displayed as completed/Yes when the bank,cost and Rebate section is not added. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 19/07/2016 16:34:09 | 20/07/2016 14:47:44 | 21/07/2016 17:48:17
76 | 76 | Scheme Management | Sprint4 | MDM: Getting server error while clicking on Manage scheme- Unable to process with testing. | Code | Data Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 19/07/2016 16:53:38 | 22/07/2016 23:08:36 | 23/07/2016 18:13:42
77 | 77 | Authentication & Authorization | Sprint1 | UM: User Name should be Alphanumeric characters include (A-Z, a-z, 0-9) without space in between any characters. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 19/07/2016 17:45:11 | 19/07/2016 19:10:03 | 21/07/2016 15:17:26
78 | 78 | Scheme Management | Sprint2 | MDM: Add scheme- User should not be able to add any scheme without completing all the sections( say-schedule of land development) | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 19/07/2016 18:38:58 | 20/07/2016 14:46:52 | 21/07/2016 17:47:41
79 | 79 | Property Management | Sprint2 | MDM: For any new scheme unable to calculate the total property cost correctly and also the sector is not populating correctly while adding the property. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 4 | Closed |  | 20/07/2016 12:59:57 | 21/07/2016 19:42:51 | 22/07/2016 19:24:46
80 | 80 | Scheme Management | Sprint2 | MDM: Unable to add scheme with Department as Housing. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 20/07/2016 16:33:24 | 20/07/2016 18:49:13 | 21/07/2016 17:42:39
81 | 81 | Scheme Management | Sprint2 | MDM: Manage circle rate issue ( heading name missing)- User is unable to enter the data as per the formula (The Circle rate duration is not End date of circle rate = [Start date of new circle rate-1]) | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 20/07/2016 17:17:31 | 21/07/2016 14:38:49 | 21/07/2016 19:01:02
82 | 82 | View Application Details | Sprint3 | Allotment-The user should be able to see the bank which is added during during scheme while adding a new application. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 20/07/2016 17:59:13 | 27/07/2016 13:06:01 | 2016-01-08 17:37
83 | 83 | View Application Details | Sprint3 | Alotment: Random issue-Unable to view the schemes while adding any application. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 20/07/2016 18:03:12 | 27/07/2016 13:00:15 | 2016-03-08 18:20
84 | 84 | Add Application Details | Sprint3 | Allotment: Regression testing issues. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 20/07/2016 18:10:41 | 27/07/2016 17:02:46 | 2016-02-08 11:13
85 | 85 | Edit Allotted Property | Sprint3 | Allotment- Edit Allotment Details: User is unable to edit the 'Installment Start Date' | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 2 | Closed |  | 20/07/2016 19:01:15 | 22/07/2016 21:17:05 | 23/07/2016 18:26:38
86 | 86 | Approve/Reject request | Sprint3 | Allotment: User is not able to reject any application also not able to approve when aprover give comments ( =characters) | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 21/07/2016 11:33:11 | 21/07/2016 14:16:05 | 22/07/2016 19:47:35
87 | 87 | Generate an Allotment Letter | Sprint3 | Allotment : Through out the application-The format and the print content should be properly aligned and should be displayed properly. | Design | UI Design Issue | Mankaran Singh Kohli | 2 - High | 3 | Active |  | 21/07/2016 12:03:44
88 | 88 | View Allottee List | Sprint3 | Allotment: The approve list should be displayed department wise. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 21/07/2016 12:34:26 | 22/07/2016 10:41:14 | 22/07/2016 19:24:02
89 | 89 | Add Application Details | Sprint3 | Allotment: All the details as entered during adding a scheme should displayed correctly throughout the application ( ex- Block, Department- Commercial) | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 21/07/2016 13:18:04 | 2016-02-08 13:23 | 2016-03-08 16:27
90 | 90 | Manage Notification | Sprint2 | MDM: Add notification is not working. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 21/07/2016 18:33:42 | 26/07/2016 12:12:39 | 2016-01-08 16:25
91 | 91 | Property Management | Sprint2 | Allotment: Notification is not working for Refund/Approve/Reject. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 22/07/2016 10:59:19 | 27/07/2016 17:51:45 | 2016-01-09 12:32
92 | 92 | Property Management | Sprint2 | MDM: Add Property Screen- User is not able to add any property in case clicks on Add button twice. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 4 | Closed |  | 22/07/2016 13:43:46 | 22/07/2016 19:46:19 | 23/07/2016 18:19:20
93 | 93 | Add Application Details | Sprint3 | Allotment( Backlog) :Add Application: Duplicate application should not be created upon double click and also the Form should be unique department wise for any scheme. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 22/07/2016 16:23:15 | 26/07/2016 11:45:37 | 2016-01-08 17:27
94 | 94 | Edit Application Details | Sprint3 | Allotment: Doubts/ suggestions: allotment date should not be a past date of any scheme . | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 3 | Closed |  | 22/07/2016 17:37:47 | 27/07/2016 17:52:01 | 29/08/2016 17:30:11
95 | 95 | Manage Notification | Sprint2 | MDM: Add property screen: Add button gets disabled while adding a new property. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 23/07/2016 14:54:15 | 27/07/2016 12:58:50 | 2016-01-08 16:25
96 | 96 | Scheme Management | Sprint2 | MDM: Unable to view the previous scheme on 'Manage Applications' screen when I create a new scheme and navigate till Manage Applications screen. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 1 | Closed |  | 23/07/2016 18:05:19 | 27/07/2016 13:06:18 | 2016-01-08 17:03
97 | 97 | View Allottee List | Sprint3 | Allotment: Draftr allottee list screen : Duplicate row gets displayed for the same scheme. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 25/07/2016 13:38:09 | 26/07/2016 18:31:52 | 2016-01-08 17:37
98 | 98 | Manage Refund | Sprint2 | MDM: Edit Refund - Getting server error while updating a refund. | Code | Data Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 25/07/2016 17:23:08 | 26/07/2016 13:05:54 | 2016-01-08 16:26
99 | 99 | View Allottee List | Sprint3 | Allotment:View Allotment : User is not able to view the fields' value as entered for any allotment. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 25/07/2016 18:05:00 | 26/07/2016 11:34:20 | 2016-01-08 17:29
100 | 100 | Initiate Refund for Unsuccessful Applicants | Sprint3 | Allotment- Refund is not working- Getting server error. | Code | Data Error | Dhananjay Kaushik | 2 - High | 1 | Closed |  | 26/07/2016 12:21:20 | 26/07/2016 13:15:41 | 27/07/2016 17:32:57
101 | 101 | Allotment of Property | Sprint3 | Allotment: Add Allotment Details- Getting server error while user clicks( twice) on Add button. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 27/07/2016 14:06:02 | 27/07/2016 17:51:39 | 2016-01-08 17:02
102 | 102 | View Allottee List | Sprint3 | Allotment: Allottee List Request screen : Duplicate RID should not be generated. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 27/07/2016 15:48:07 | 27/07/2016 17:33:56 | 2016-01-09 12:23
103 | 103 | Approve/Reject request | Sprint3 | Allotment: The Approved on date should be displayed as per the approval/ reject of any application. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 27/07/2016 16:03:18 | 27/07/2016 20:19:57 | 2016-01-08 17:11
104 | 104 | Initiate Refund for Unsuccessful Applicants | Sprint3 | Allotment: Refunds - Unsuccessful Applicants- Unable to initiate refund for any unsuccessful applicants | Code | Logic Error | Vishal Shukla | 2 - High | 3 | Active |  | 27/07/2016 16:56:56
105 | 105 | Initiate Refund for Unsuccessful Applicants | Sprint3 | Allotment: Unsuccessfull Applicant List Request - Getting error by clicking on approve button. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 4 | Closed |  | 27/07/2016 17:13:19 | 27/07/2016 17:36:37 | 2016-01-08 17:30
106 | 106 | Property Management | Sprint2 | Add property screen: Getting server error while clicking on Add button and cancel button. | Code | Logic Error | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 27/07/2016 19:01:00 | 28/07/2016 12:05:15 | 2016-01-08 15:47
107 | 107 | View Application Details | Sprint3 | Allotment: The company name is not displaying on manage application screen. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-02-08 11:34 | 2016-03-08 19:07 | 29/08/2016 13:19:29
108 | 108 | Edit Application Details | Sprint3 | Allotment: Edit Application/ Add application- An appropriate message should be displayed upon invalid entry for any fields. | Code | Text Message | Dhananjay Kaushik | 3 - Medium | 4 | Closed |  | 2016-02-08 11:55 |  | 2016-01-09 12:29
109 | 109 | Edit Application Details | Sprint3 | Allotment: Edit allotment- Error message should not come while editing any allotment. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Closed |  | 2016-02-08 12:22 | 2016-02-08 16:17 | 2016-01-09 12:26
110 | 110 | Allotment of Property | Sprint3 | Allotment: The form number should be unique for a scheme department wise. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 2016-02-08 14:44 | 2016-04-08 17:19 | 2016-01-09 12:33
111 | 111 | Create Allottee List of a scheme | Sprint3 | Allotment: Draft Allottee list: The status is not changing as per the transaction ( approval/ reject) | Code | Logic Error | Vishal Shukla | 2 - High | 3 | Active |  | 2016-02-08 15:43
112 | 112 | View Allotment Property | Sprint3 | Allotment: Property Details- The allotment money Civil cost and property cost are not displaying as per the requirement. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 2016-02-08 18:03 | 2016-03-08 14:12 | 2016-03-08 16:15
113 | 113 | Add lease deed | Sprint3 | Lease deed: User should not be able to “Add Lease Deed” when dues are available on Payments. | Code | Logic Error | Ranjeet Singh | 3 - Medium | 2 | Closed |  | 2016-03-08 15:04 | 2016-03-08 17:24 | 2016-03-08 21:00
114 | 114 | Create Scheme | Sprint4 | Suggestion: The location section should not be available for housing department. | Code | Business Rule | Dhananjay Kaushik | 4 - Low | 4 | Resolved |  | 2016-03-08 16:06 | 2016-03-08 17:49
115 | 115 | Generate Lease Rent Challan | Sprint4 | Lease Deed: User is not able to find correct amount on Lease rent challan | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-03-08 19:12 | 2016-08-08 10:49
116 | 116 | View Lease Deed Details | Sprint4 | Lease deed: Dues are not correct in payment schedule section. | Code | Logic Error | Ranjeet Singh | 3 - Medium | 2 | Closed |  | 2016-04-08 15:54 | 2016-05-08 16:59 | 2016-08-08 16:19
117 | 117 | View Lease Deed Details | Sprint4 | Lease Deed: Allotment money should be displayed instead Yes on checklist. | Code | Logic Error | Vishal Shukla | 3 - Medium | 2 | Active |  | 2016-04-08 16:59
118 | 118 | Add Lease Deed Details | Sprint4 | Lease deed: Document required list should be available on the checklist pop up/ RID: 77 | Code | Logic Error | Vishal Shukla | 3 - Medium | 2 | Active |  | 2016-04-08 17:05
119 | 119 | Add Lease Deed Details | Sprint4 | Lease Deed: User should not be able to select checklist date before allotment date | Code | Logic Error | Ranjeet Singh | 3 - Medium | 2 | Closed |  | 2016-04-08 17:08 | 22/08/2016 13:18:01 | 24/08/2016 13:14:31
120 | 120 | Add Mutation/Substitution SMS/Email Notifications to requestor | Sprint4 | Mutation: Add Mutation Request screen - User is not able to add the mutation request. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Resolved |  | 2016-05-08 16:02 | 2016-05-08 16:12
121 | 121 | Approve/Reject Mutation approval Request | Sprint4 | Mutation: Add Mutation Request screen - User should not be allowed to send for approval of any mutation request to an admin who is not having right to that department. | Code | Business Rule | Dhananjay Kaushik | 2 - High | 3 | Resolved |  | 2016-05-08 16:32 | 2016-08-08 14:38
122 | 122 | Approve/Reject Mutation approval Request | Sprint4 | Mutation: View Mutation Request screen issue: RID and transfer date are not displaying as entered. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Resolved |  | 2016-05-08 17:47 | 2016-08-08 14:45
123 | 123 | Add Possession Order | Sprint4 | Possession: User is not able to add possession entry. Application gets crashed. | Code | Missing Function | Dhananjay Kaushik | 1 - Critical | 1 | Closed |  | 2016-05-08 19:02 | 19/08/2016 17:36:30 | 24/08/2016 14:24:29
124 | 124 | Add Possession Order | Sprint4 | Possession: User should be able to add possession order for his department only | Code | Business Rule | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:05 | 19/08/2016 17:37:50
125 | 125 | Add Possession Order | Sprint4 | Possession: User should not be able to add possession order for RID which has already added possession order and an alert msg should be generated. | Code | Business Rule | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:08 | 22/08/2016 16:50:32
126 | 126 | Add Possession Order | Sprint4 | Possession: System should generate a message when user clicks on Add button on 'add possession order' page | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:11 | 22/08/2016 16:51:21
127 | 127 | Add Possession Order | Sprint4 | Possession: Wrong message is displayed and filled information is not reset when user selects select after selecting RID in the RID dropdown on 'Add possession order' page | Code | Text Message | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:14 | 22/08/2016 14:54:59
128 | 128 | Allotment of Property | Sprint4 | Possession : When area of a property is changed during possession, Area change column in grid contains ‘Yes’, else it should contain ‘No’ | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:18 | 26/08/2016 12:59:50
129 | 129 | Add Possession Order | Sprint4 | Possession: In case of company, • Signing Authority • Registered office not available | Code | Logic Error | Ranjeet Singh | 3 - Medium | 2 | Closed |  | 2016-05-08 19:22 | 22/08/2016 13:28:21 | 25/08/2016 13:49:54
130 | 130 | Add bulk Possession Order | Sprint4 | Possession: Wrong message is displayed when user clicks on 'add' button on 'add bulk possession order' page after selecting scheme and department | Code | Text Message | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 19:34 | 26/08/2016 12:39:08
131 | 131 | Add Lease Deed Details | Sprint4 | Lease deed: Lease deed execution date should always be after allotment date on add lease deed page. | Code | Business Rule | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 2016-05-08 21:00 | 25/08/2016 10:39:00
132 | 132 | Edit Application Details | Sprint4 | Checklist: Checklist date should not before allotment date | Code | Business Rule | Ranjeet Singh | 3 - Medium | 2 | Closed |  | 2016-05-08 21:16 | 2016-08-08 14:56 | 24/08/2016 13:11:53
133 | 133 | Allotment of Property | Sprint4 | Page should get refreshed when user selects 'select' option in the RID drop down on checklist page. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 24/08/2016 13:32:26 | 24/08/2016 17:30:29
134 | 134 | Add Possession Order | Sprint5 | Possession: Possession details are not captured on Add Possession Entry page. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 24/08/2016 14:28:18 | 26/08/2016 20:29:26
135 | 135 | Allotment of Property | Sprint3 | Allotment: Property Details screen : Unable to view the Applicant Details (ex- Department Name -Housing) | Code | Logic Error | Vishal Shukla | 2 - High | 3 | Active |  | 24/08/2016 17:47:56
136 | 136 | Add Mortgage Request | Sprint5 | Add Mortgage screen : Spelling mistakes / Display issue & Validation issue. | Design | UI Design Issue | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 25/08/2016 12:53:24 |  | 2016-01-09 17:55
137 | 137 | Add Mortgage Request | Sprint5 | Add Mortgage: User should not be allowed to Add Mortgage in case there is " Total Dues> 0 ( say 7678 INR). | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Closed |  | 25/08/2016 13:56:01 | 25/08/2016 17:19:45 | 2016-01-09 18:00
138 | 138 | Cancel mortgage request | Sprint5 | Mortgage Request screen : For cancelled requests user should get the option to ‘resubmit Request’. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 25/08/2016 15:41:42 | 25/08/2016 17:19:08 | 2016-01-09 18:03
139 | 139 | Add Mortgage Request | Sprint5 | Mortgage Request screen : User is unable to click on ‘Generate Mortgage’ button on mortgage request screen. | Code | Logic Error | Ambrish Verma | 3 - Medium | 3 | Active |  | 25/08/2016 16:14:04
140 | 140 | Request Functional Approval | Sprint5 | Functional : Add Functional Request- Unable to Submit any request for approval. | Code | Partial Implemented | Dhananjay Kaushik | 1 - Critical | 2 | Closed |  | 25/08/2016 17:35:38 | 25/08/2016 19:01:39 | 26/08/2016 12:34:21
141 | 141 | Add Rent Permission Request | Sprint5 | Rent Permission: Unable to do testing for rent permission as Functional is not working ( BUG 140) | Code | Partial Implemented | Vishal Shukla | 2 - High | 2 | Active |  | 25/08/2016 18:22:19
142 | 142 | Add Building Plan Approval Request | Sprint5 | Completion: Information is not available when user selects RID from the RID drop down on 'add completion request' page. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 25/08/2016 19:31:13 | 26/08/2016 18:43:27
143 | 143 | Add Building Plan Approval Request | Sprint5 | Completion: 'Completion Time From' is not available on the page. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 25/08/2016 19:34:10 | 26/08/2016 13:15:13
144 | 144 | Add Building Plan Approval Request | Sprint5 | Completion: Download button is not available on new page. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 25/08/2016 19:37:19 | 29/08/2016 14:39:18
145 | 145 | Add Building Plan Approval Request | Sprint5 | Completion: Download button is not available. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 2 | Resolved |  | 25/08/2016 19:41:05 | 29/08/2016 14:39:55
146 | 146 | Request Functional Approval | Sprint5 | Manage Functional Properties : Suggestion- Either the date should not be visible in case of rejection/ In progress or the status should be displayed properly. | Code | Business Rule | Dhananjay Kaushik | 3 - Medium | 3 | Resolved |  | 26/08/2016 15:15:15 | 2016-02-09 16:28
147 | 147 | Request Functional Approval | Sprint5 | Functional: User is unable to perform 'Functional' then transfer followed by functional correctly as the department & other details are not displaying as entered. | Code | Partial Implemented | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 26/08/2016 15:19:03 | 29/08/2016 12:12:49 | 2016-01-09 17:30
148 | 148 | Request Functional Approval | Sprint5 | Add Functional Request : Field level Validation & The fields name are not displaying as per the requirement. | Code | Logic Error | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 26/08/2016 15:49:31 | 29/08/2016 13:24:46 | 2016-01-09 16:21
149 | 149 | Request Functional Approval | Sprint5 | Add Functional Request : User would also have the option to upload any of the document | Code | Missing Function | Vishal Shukla | 3 - Medium | 3 | Active |  | 26/08/2016 15:52:28
150 | 150 | View Request- Department User | Sprint5 | View Functional Request : The user should not be allowed to enter the comment> 500 while rejecting any application. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 26/08/2016 16:03:08 | 26/08/2016 17:45:07 | 2016-01-09 16:32
151 | 151 | View Request- Department User | Sprint5 | View Functional Request : An appropriate message should be displayed when user clicks on submit button while selecting the approver name. | Code | Text Message | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 26/08/2016 16:18:05 | 26/08/2016 18:22:19 | 2016-01-09 16:27
152 | 152 |  | Sprint5 | View Functional Request : User should get documents details. | Code | Logic Error | Anuj Kumar | 3 - Medium | 3 | Active |  | 26/08/2016 17:08:45
153 | 153 | View Request- Department User | Sprint5 | View Functional Request : The comment date is not displayed in view comment form . | Code | Data Error | Dhananjay Kaushik | 4 - Low | 4 | Closed |  | 26/08/2016 17:33:11 | 26/08/2016 18:47:46 | 2016-01-09 16:34
154 | 154 | View Request- Department User | Sprint5 | View Functional Request : Generate functional certificate & The functional charge should work properly and displayed on 'Manage Functional Properties screen' | Code | Partial Implemented | Anuj Kumar | 2 - High | 2 | Active |  | 26/08/2016 17:50:51
155 | 155 | Add Rent Permission Request | Sprint5 | Rent Request: Edit Rent Request screen : User is not able to Resubmit for approval. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 29/08/2016 12:00:18 | 29/08/2016 12:11:56 | 2016-01-09 18:39
156 | 156 | Add Rent Permission Request | Sprint5 | Rent request: Manage rent request: In case of gender as Company the Father's name shouldn't be displayed. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Closed |  | 29/08/2016 12:07:48 | 29/08/2016 13:43:58 | 2016-01-09 18:47
157 | 157 | Submit Allottee list for approval | Sprint3 | Add Allotment: User is not able to select Occupation( Mandatory field) for Gender as company. | Code | Logic Error | Shatrughna Kumar | 3 - Medium | 2 | Active |  | 29/08/2016 13:10:25
158 | 158 | Add Rent Permission Request | Sprint5 | Rent Request: Unable to do testing for Rent Request as the data is not coming correctly for functional. | Code | Partial Implemented | Dhananjay Kaushik | 2 - High | 2 | Closed |  | 29/08/2016 14:16:25 | 29/08/2016 15:07:05 | 2016-01-09 18:51
159 | 159 | Add property | Sprint2 | Add property: suggestion- The Property no Should not be zero( The Property should be unique for same department, sector & block ) | Code | Business Rule | Naresh Kumar | 4 - Low | 3 | Active |  | 2016-01-09 10:55
160 | 160 | Add Lease Deed Details | Sprint4 | Add lease deed: User is not able to to add lease deed. | Code | Logic Error | Ajay Pratap Solanki | 1 - Critical | 2 | Active |  | 2016-01-09 13:24
161 | 161 | View Request- Department User | Sprint5 | MANAGE RENT PERMISSION: The view comment should be un editable in all the case Canceled/ Approved/ Rejection and should be displayed with data. | Code | Logic Error | Dhananjay Kaushik | 2 - High | 3 | Resolved |  | 2016-01-09 18:30 | 2016-02-09 17:09
162 | 162 | Add Rent Permission Request | Sprint5 | MANAGE RENT PERMISSION : The fields should be displayed as per the requirement , Mandatory fields with (*) and in case of blank an appropriate message should be displayed. | Design | UI Design Issue | Shatrughna Kumar | 3 - Medium | 3 | Active |  | 2016-02-09 12:34
163 | 163 | Add Rent Permission Request | Sprint5 | MANAGE RENT PERMISSION: Getting server error while clicking on 'Resubmit for approval' while resubmitting a cancelled request. | Code | Logic Error | Shatrughna Kumar | 2 - High | 3 | Active |  | 2016-02-09 13:03
164 | 164 | Add Rent Permission Request | Sprint5 | MANAGE RENT REQUEST: The Renting Date and Renting end date should not display with time. | Design | UI Design Issue | Dhananjay Kaushik | 4 - Low | 4 | Resolved |  | 2016-02-09 13:19 | 2016-02-09 15:07
165 | 165 | Cancel rent permission request | Sprint5 | MANAGE RENT PERMISSION: Upon a request is rejected by the approver the user should not get the option of ‘Cancel Request’. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 3 | Resolved |  | 2016-02-09 13:34 | 2016-02-09 15:20
166 | 166 | Approve/Reject Rent Permission Request | Sprint5 | MANAGE RENT REQUEST : In the case of approval the comment is not mandatory to fill by an approver. | Code | Logic Error | Dhananjay Kaushik | 3 - Medium | 4 | Resolved |  | 2016-02-09 13:53 | 2016-02-09 15:15
167 | 167 | Approve/Reject Rent Permission Request | Sprint5 | MANAGE RENT PERMISSION: User is able to approve request in spite the renting charge is not paid. | Code | Logic Error | Shatrughna Kumar | 2 - High | 1 | Active |  | 2016-02-09 14:55

## RCAINS
Internal Testing |  |  | UAT Error
Requirement | Design | Code | Testing | Enhancement | Change Request | Environmental Issue
Requirement not clear | Compatibility Issue | Requirement Not Implemented | Environmental Issue | Requirement Missing | New Functionality | Configuration Issue
Requitrement GAP | UI Design Issue | Partial Implemented | Requirement Not clear | Minor Change |  | Data Migration Issue
| Impact Analysis Not Done | Text Message | Insuffiecient Test Cases |  |  | Partially Deployed
Data Error
Logic Error
Business Rule
Missing Function
Name | Range Address
Requirement | E7:E13
Design | F7:F12
Code | G7:G13
Testing | H7:H13
Enhancement | I7:I13
Change_Request | J7:J13
Environmental Issue | K7:K18
L7:L13
M7:N13