## Review Records Log Instruction
Review Records Log Instructions
Field | Description
Review Number | Unique identifier for the Review, i.e., 1,2 etc.
Created By | Name of the person who reported the Review.
Review Description | Description of the Review. State the subsystem, area, or other part of the product in which the Review occurs or which is affected by the Review.
Lifecycle Phase | List the lifecycle this Review was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this Review on the project:
H = High (extremely important, the project cannot be successful without this Review being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the Review is not resolved)
Owner | Name of the person who is responsible for fixing the Review.
Assigned Date | Date on which the Review was assigned for resolution.
Status | Current status of the Review: New, In Progress, Under Review and Completed.
Resolution Date | Date on which the Review is to be resolved (or is resolved depending upon its status).

## Sheet1
Priority | Count of Priority
High | 24
Low | 13
Medium | 120

## Review Records Log
Review Records Log
Project Name | PMIS(Noida project)
Project Manager | Vishal Shukla
Review No. | Created By | Review Description | Lifecycle Phase | Priority | Owner | Assigned Date | Status | Resolution Date | Status | Priority | PM | Lifecycle Phase
1 | Rahul | Risk Owner is not identified | PMP | High | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15 | New
2 | Rahul | It was discussed during project kickoff that Cloud Infrastructure will be used for System Testing. This should be part of Testing environment. | PMP | Medium | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15 | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | Rahul | Use case list is not updated | PMP | High | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15 | In Progress | Medium | Initiating | Concept
4 | Akshay Kumar Das | Details of the class diagram is missing | Design | Low | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
5 | Akshay Kumar Das | Hansen details are not mentioned | Design | Medium | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
6 | Akshay Kumar Das | Configuration sectoin is missing | Design | High | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
7 | Akshay Kumar Das | Remove Cue Me architecture diagram because it is too comples to understand | Design | Medium | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
8 | Dhananjay Kumar | I spoke with Krish and Steve earlier regarding the proposed project timeline. We agreed that it’ll be best to release both the Complaints and Notification modules together in January | MPP | Low | Vishal Shukla | 2016-04-08 | Closed | 2016-04-04
9 | Rahul | Risk Owner is not identified | PMP | High | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15
10 | Rahul | It was discussed during project kickoff that Cloud Infrastructure will be used for System Testing. This should be part of Testing environment. | PMP | Medium | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15
11 | Rahul | Use case list is not updated | PMP | High | Vishal Shukla | 2016-03-09 | Closed | 2016-03-15
12 | Akshay Kumar Das | Details of the class diagram is missing | Design | Low | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
13 | Akshay Kumar Das | Hansen details are not mentioned and Integration with other system for ACP5 is missing | Design | Medium | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
14 | Akshay Kumar Das | Configuration sectoin is missing | Design | High | Ajay Pratap Solanki | 2016-04-18 | Closed | 2016-04-21
15 | Akshay Kumar Das | Remove Cue Me architecture diagram because it is too complex to understand | Design | Medium | Ajay Pratap Solanki | 2016-05-24 | Closed | 2016-05-28
16 | Dhananjay Kumar | I spoke with Krish and Steve earlier regarding the proposed project timeline. We agreed that it’ll be best to release both the Complaints and Notification modules together in January | MPP | Low | Vishal Shukla | 2016-04-08 | Closed | 2016-04-04
17 | Akshay Kumar Das | In screen shot it is missing, Please put a header of grid. | Design | Medium | Ajay Pratap Solanki | 2016-05-24 | Closed | 2016-05-28
18 | Akshay Kumar Das | Wireframe inserted in Figure 114 : Assign ACP5 Case – ACP5 Details | Design | High | Ajay Pratap Solanki | 2016-05-24 | Closed | 2016-05-28
19 | Akshay Kumar Das | Figure 83 : Review Notification - History wirefram added in 3.23.6 | Design | High | Ajay Pratap Solanki | 2016-05-24 | Closed | 2016-05-28
20 | Vishal Shukla | Revove unused files | Code Review | Medium | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
21 | Vishal Shukla | Remove unused referecnes | Code Review | Medium | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
22 | Vishal Shukla | Delete unsued folder | Code Review | High | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
23 | Vishal Shukla | Remove unused referecnes | Code Review | High | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
24 | Vishal Shukla | Remove unused namespaces in all the files of project | Code Review | High | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
25 | Vishal Shukla | Folder naming convention is not consistent | Code Review | Low | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
26 | Vishal Shukla | Remove unused dll referecnes | Code Review | High | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
27 | Vishal Shukla | Use Property getter to instanciate objects intead of class constructor | Code Review | Medium | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
28 | Vishal Shukla | Use depency injection to manage Dbcontext object instead of crearting it inside methods | Code Review | Medium | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
29 | Vishal Shukla | User dependency injection for respotiory objects | Code Review | Medium | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
30 | Vishal Shukla | User dependency injection for service objects | Code Review | Medium | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
31 | Vishal Shukla | Remove commented code | Code Review | Low | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
32 | Vishal Shukla | Insert class level comments | Code Review | Low | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
33 | Vishal Shukla | Insert method level comments | Code Review | Low | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
34 | Vishal Shukla | Insert comments for specific logic used in code | Code Review | Medium | Naresh Kumar | 2016-04-21 | Closed | 2016-04-29
35 | Vishal Shukla | Create region to separate related code. Ex. Separate region for Private and Public methods | Code Review | Medium | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
36 | Vishal Shukla | Use views to create HTML istead of creating html in code | Code Review | Low | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
37 | Vishal Shukla | User dependency injection for service objects | Code Review | Medium | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
38 | Vishal Shukla | Wherever possible use constants/resources instead of hardcoded strings | Code Review | Medium | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
39 | Vishal Shukla | use string.empty instead of "" string | Code Review | High | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
40 | Vishal Shukla | use string.format or stringbuilder instead + operator for concatenation | Code Review | High | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
41 | Vishal Shukla | Remove empty try catch, no need to throw exception, it creates overhead | Code Review | High | Mankaran Singh Kohli | 2016-04-21 | Closed | 2016-04-29
42 | Vishal Shukla | Dispose DEPDBEntities, better use dependency injection | Code Review | High | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
43 | Vishal Shukla | Remove "TODO: Pending Implementation" lines | Code Review | Low | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
44 | Vishal Shukla | for App Setting use class ConfigurationManager.AppSetting, Its recommended to have a single setting class which has all app setting property. | Code Review | Low | Ambrish Verma | 2016-04-21 | Closed | 2016-04-29
45 | Vishal Shukla | use Dbfunction instead of EntityFunctions, EntityFunctions is obsolete | Code Review | Low | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
46 | Vishal Shukla | remove unused variables _generalService | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
47 | Vishal Shukla | modelInspectionDetails.IsInsFollowUp != null, Boolean cant be null | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
48 | Vishal Shukla | roleId != null,User_Id != null int cant be null | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
49 | Vishal Shukla | inspectionObj.TurnAroundTimeVal != null Boolean cant be null | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
50 | Vishal Shukla | Remove duplicate namespaces using Kendo.Mvc.Extensions; | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
51 | Vishal Shukla | string comma = ""; , string menuIdSiteMapper = ""; remove unused variables | Code Review | High | Ajay Pratap Solanki | 2016-05-12 | Closed | 2016-05-20
52 | Vishal Shukla | bool flag = false;,ifSuccess = false;,int loginId = 1002; remove unused variables | Code Review | High | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
53 | Vishal Shukla | duplicate member InspectionId | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
54 | Vishal Shukla | User Keno DataSourceRequest object .ToDataSourceResult(request) method instead of ToList() | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
55 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Common.Constants' | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
56 | Vishal Shukla | Name 'Complaint_Type' does not match rule 'Fields (not private)'. Suggested name is 'ComplaintType'. | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
57 | Vishal Shukla | Name 'statusObj' does not match rule 'Methods, properties and events'. Suggested name is 'StatusObj'. | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
58 | Vishal Shukla | Name 'responseObj' does not match rule 'Methods, properties and events'. Suggested name is 'ResponseObj'. | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
59 | Vishal Shukla | Name 'statusId' does not match rule 'Methods, properties and events'. Suggested name is 'StatusId'. | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
60 | Vishal Shukla | Name 'statusMessage' does not match rule 'Methods, properties and events'. Suggested name is 'StatusMessage'. | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
61 | Vishal Shukla | Name '_status' does not match rule 'Parameters'. Suggested name is 'status'. | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
62 | Vishal Shukla | Initializing field by default value is redundant | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
63 | Vishal Shukla | Name '_UserId' does not match rule 'Local variables'. Suggested name is 'userId'. | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
64 | Vishal Shukla | Type cast is redundant | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
65 | Vishal Shukla | Expression is always true | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
66 | Vishal Shukla | Comparison with true is redundant | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
67 | Vishal Shukla | Name 'InspectionObj' does not match rule 'Parameters'. Suggested name is 'inspectionObj'. | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
68 | Vishal Shukla | Replace with single call to FirstOrDefault(..) | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
69 | Vishal Shukla | Statement is not terminated | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
70 | Vishal Shukla | Redundant explicit array type specification | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
71 | Vishal Shukla | Element 'u' is obsolete or nonstandard | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
72 | Vishal Shukla | Element 'font' is obsolete or nonstandard | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
73 | Vishal Shukla | Not all code paths return a value | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
74 | Vishal Shukla | Condition is always 'true'. | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
75 | Vishal Shukla | Local variable 'InspectionId' is never used | Code Review | Medium | Ambrish Verma | 2016-05-12 | Closed | 2016-05-20
76 | Vishal Shukla | '==' tries to coerce values before comparing them which can lead to some unexpected results | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
77 | Vishal Shukla | Duplicate property declaration | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
78 | Vishal Shukla | Parameter 'err' is never used | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
79 | Vishal Shukla | Block is redundant | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
80 | Vishal Shukla | Replace with single call to FirstOrDefault(..) | Code Review | Medium | Mankaran Singh Kohli | 2016-05-12 | Closed | 2016-05-20
81 | Vishal Shukla | '==' tries to coerce values before comparing them which can lead to some unexpected results | Code Review | Medium | Naresh Kumar | 2016-05-12 | Closed | 2016-02-12
82 | Vishal Shukla | Name 'Id' does not match rule 'Function Parameter'. Suggested name is 'id'. | Code Review | Medium | Naresh Kumar | 2016-05-12 | Closed | 2016-02-12
83 | Vishal Shukla | Condition is always 'true'. | Code Review | Medium | Naresh Kumar | 2016-05-12 | Closed | 2016-02-12
84 | Vishal Shukla | Name 'User_Id' does not match rule 'Local Variable'. Suggested name is 'userId'. | Code Review | Medium | Naresh Kumar | 2016-05-12 | Closed | 2016-02-12
85 | Vishal Shukla | Unit of measure is redundant | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
86 | Vishal Shukla | Redundant explicit array type specification | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
87 | Vishal Shukla | The property 'opacity' is not compatible with Internet Explorer 8.0 | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
88 | Vishal Shukla | Duplicate declaration | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
89 | Vishal Shukla | Replace with single call to FirstOrDefault(..) | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
90 | Vishal Shukla | Possible 'System.NullReferenceException' | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
91 | Vishal Shukla | Catch clause is redundant | Code Review | High | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
92 | Vishal Shukla | Empty statement is redundant | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
93 | Vishal Shukla | Redundant explicit array type specification | Code Review | Medium | Shatrughn Kumar | 2016-06-14 | Closed | 2016-06-23
94 | Vishal Shukla | Name 'CaseType' does not match rule 'Local Variable'. Suggested name is 'caseType'. | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
95 | Vishal Shukla | '==' tries to coerce values before comparing them which can lead to some unexpected results | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
96 | Vishal Shukla | Statement is not terminated | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
97 | Vishal Shukla | Return statement should have value | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
98 | Vishal Shukla | Not all code paths return a value | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
99 | Vishal Shukla | Name 'ComplaintPreviewURL' does not match rule 'Function Parameter'. Suggested name is 'complaintPreviewUrl'. | Code Review | Medium | Ajay Pratap Solanki | 2016-06-14 | Closed | 2016-06-23
100 | Vishal Shukla | Use of an implicitly declared global variable 'CaseType' | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
101 | Vishal Shukla | Field can be made readonly | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
102 | Vishal Shukla | '?:' expression can be re-written as '??' expression | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
103 | Vishal Shukla | Replace with single call to FirstOrDefault(..) | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
104 | Vishal Shukla | Possible 'System.NullReferenceException' | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
105 | Vishal Shukla | Loop can be converted into LINQ-expression | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
106 | Vishal Shukla | Possible 'System.InvalidOperationException' | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
107 | Vishal Shukla | Expression is always true | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
108 | Vishal Shukla | Redundant 'Object.ToString()' call | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
109 | Vishal Shukla | Initializing field by default value is redundant | Code Review | Medium | Anuj Kumar | 2016-06-14 | Closed | 2016-06-23
110 | Vishal Shukla | Field can be made readonly | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
111 | Vishal Shukla | Local variable 'loginId' is only assigned but its value is never used | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
112 | Vishal Shukla | '==' tries to coerce values before comparing them which can lead to some unexpected results | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
113 | Vishal Shukla | Duplicate declaration | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
114 | Vishal Shukla | Use of an implicitly declared global variable 'esri' | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
115 | Vishal Shukla | Statement is not terminated | Code Review | Medium | Ambrish Verma | 2016-06-14 | Closed | 2016-06-23
116 | Vishal Shukla | Rewrite as 'DateTime?' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
117 | Vishal Shukla | '?:' expression can be re-written as '??' expression | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
118 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Repositories.Compliants' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
119 | Vishal Shukla | Possible 'System.NullReferenceException' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
120 | Vishal Shukla | Name 'Todate' does not match rule 'Parameters'. Suggested name is 'todate'. | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
121 | Vishal Shukla | Cannot resolve symbol 'isFollow' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
122 | Vishal Shukla | Parameter 'complaintId' has no matching param tag in the XML comment for DEP.Asbestos.UI.ComplaintsController.BtnClose (but other parameters do) | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
123 | Vishal Shukla | Join declaration and assignment | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
124 | Vishal Shukla | Possible 'System.NullReferenceException' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
125 | Vishal Shukla | Redundant 'Object.ToString()' call | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
126 | Vishal Shukla | Empty statement is redundant | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
127 | Vishal Shukla | Local variable 'currentuserDetails' is never used | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
128 | Vishal Shukla | Name 'GetNOVsByInspection' does not match rule 'Methods, properties and events'. Suggested name is 'GetNoVsByInspection'. | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
129 | Vishal Shukla | Name 'ViewType' does not match rule 'Parameters'. Suggested name is 'viewType'. | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
130 | Vishal Shukla | '==' tries to coerce values before comparing them which can lead to some unexpected results | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
131 | Vishal Shukla | Parameter 'obj' is never used | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
132 | Vishal Shukla | Variable 'responTmHrs' is used outside of block which it is declared | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
133 | Vishal Shukla | Unknown CSS class 'compNumLink' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
134 | Vishal Shukla | Cannot resolve section 'scripts' | Code Review | Medium | Mankaran Singh Kohli | 2016-07-19 | Closed | 2016-07-28
135 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Common.Constants' | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
136 | Vishal Shukla | Name 'ComplaintNumber' does not match rule 'Parameters'. Suggested name is 'complaintNumber'. | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
137 | Vishal Shukla | For-loop can be converted into foreach-loop | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
138 | Vishal Shukla | Rewrite as 'DateTime?' | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
139 | Vishal Shukla | Using directive is not required by the code and can be safely removed | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
140 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Repositories.General' | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
141 | Vishal Shukla | Content of collection 'ddlList' is never updated | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
142 | Vishal Shukla | Catch clause is redundant | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
143 | Vishal Shukla | Name 'MasterConfig_Type' does not match rule 'Parameters'. Suggested name is 'masterConfigType'. | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
144 | Vishal Shukla | Exception rethrow possibly intended | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
145 | Vishal Shukla | Local variable 'NRE' is never used | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
146 | Vishal Shukla | Using directive is not required by the code and can be safely removed | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
147 | Vishal Shukla | Initializing field by default value is redundant | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
148 | Vishal Shukla | Field can be made readonly | Code Review | Medium | Ambrish Verma | 2016-07-19 | Closed | 2016-07-28
149 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Services.General' | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
150 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Common.Logger' | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
151 | Vishal Shukla | Convert to '??' expression | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
152 | Vishal Shukla | Qualifier 'this.' is redundant | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
153 | Vishal Shukla | Name 'objILogger' does not match rule 'Static field (private)'. Suggested name is '_objILogger'. | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
154 | Vishal Shukla | Namespace does not correspond to file location, should be: 'DEP.Asbestos.Services.DI' | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
155 | Vishal Shukla | Field can be made readonly | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
156 | Vishal Shukla | Name 'provider' does not match rule 'Instance fields (private)'. Suggested name is '_provider'. | Code Review | Medium | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28
157 | Vishal Shukla | Value assigned is not used in any execution path | Code Review | Low | Anuj Kumar | 2016-07-19 | Closed | 2016-07-28