## Sheet1
ID | Title | Work Item Type | Assigned To | State | Iteration ID | Created Date | Resolved Date | Priority | Root Cause | Severity | Closed Date
28 | Manage Property screen : User is unable to add a new Property. | Bug | Dhananjay Kaushik | Closed | 4 | 2016-02-06 18:48 | 2016-08-08 16:06 | 1 | Coding Error | 2 - High | 26/08/2016 17:19:11
30 | Master data Management : Server Error in '/' Application. | Bug | Dhananjay Kaushik | Closed | 4 | 2016-02-06 18:55 | 2016-02-06 20:44 | 1 | Coding Error | 1 - Critical | 2016-06-06 15:26
34 | Master Data : Admin- getting "Server Error in '/' Application" while user is trying to 'Remove' any scheme on " Manage scheme" screen. | Bug | Dhananjay Kaushik | Closed | 4 | 2016-09-06 13:03 | 2016-09-06 18:42 | 1 | Coding Error | 1 - Critical | 17/06/2016 18:33:21
35 | Noida Authority - MDM- Admin: User is unable to edit the bank details while trying to edit an scheme. | Bug | Dhananjay Kumar | Closed | 4 | 2016-09-06 13:27 | 17/06/2016 | 3 | Coding Error | 2 - High | 19/07/2016 13:35:35
42 | UM/MDM-Tab button and Arrow button should work while adding a new property | Bug | Dhananjay Kaushik | Closed | 4 | 2016-10-06 16:18 | 2016-10-06 18:08 | 4 | Coding Error | 4 - Low | 17/06/2016 18:45:30
43 | MDM- Admin- Display issue on view property screen | Bug | Dhananjay Kaushik | Closed | 4 | 2016-10-06 16:41 | 13/06/2016 14:16:06 | 3 | Communication Error | 3 - Medium | 17/06/2016 19:00:55
44 | MDM- Admin-Display issue on Add notification and view notification. | Bug | Dhananjay Kaushik | Closed | 4 | 2016-10-06 18:16 | 13/06/2016 11:38:31 | 3 | Coding Error | 3 - Medium | 17/06/2016 18:52:14
45 | MDM- Admin-Server error while user try to enter more than 150 charecters as ' notification name and then save. | Bug | Dhananjay Kaushik | Closed | 4 | 2016-10-06 18:23 | 2016-10-06 18:45 | 3 | Coding Error | 3 - Medium | 17/06/2016 18:49:06
48 | MDM- Admin- The data from department section should not displayed once removed by clicking on remove link. | Bug | Dhananjay Kaushik | Closed | 4 | 13/06/2016 13:37:24 | 13/06/2016 13:56:51 | 2 | Coding Error | 2 - High | 17/06/2016 18:57:19
49 | MDM- Admin: Admin should not be able to add a property for ( Property/Plot No,Covered Area (Sq.Mtr) ,Floor Area Ratio ,Civil Cost,Actual Area (Sq.Mtr) and Charges (INR) =120909.00) | Bug | Dhananjay Kaushik | Closed | 4 | 13/06/2016 15:25:31 | 14/06/2016 18:38:04 | 2 | Unknown | 3 - Medium | 14/06/2016 18:38:14
50 | MDM- Admin: As appropriate error message should be displayed for ' Department*' and ' Sectors' on Add Property screen. | Bug | Dhananjay Kaushik | Closed | 4 | 13/06/2016 16:10:01 | 13/06/2016 17:39:40 | 4 | Coding Error | 3 - Medium | 17/06/2016 18:59:35
51 | MDM-Admin: Admin should be able to edit 'Deduction field on edit refund screen and server error should not come. | Bug | Dhananjay Kaushik | Closed | 4 | 13/06/2016 17:18:57 | 17/06/2016 18:30:27 | 2 | Coding Error | 2 - High | 17/06/2016 18:30:34
52 | MDM-Submit button functionality is not working upon wrong entry in Deduction and Refund Description* | Bug | Dhananjay Kaushik | Closed | 4 | 13/06/2016 18:11:55 | 2016-01-07 16:19 | 3 | Coding Error | 3 - Medium | 15/07/2016 10:43:39
53 | MDM- Admin is unable to add scheme with ( with Bank type as - Others) | Bug | Dhananjay Kaushik | Closed | 4 | 17/06/2016 14:32:02 | 28/06/2016 12:30:13 | 2 | Coding Error | 2 - High | 15/07/2016 11:05:56
55 | MDM: Calculation mistake for 'Total Property Cost (INR)' on Add Property screen. | Bug | Dhananjay Kaushik | Closed | 4 | 17/06/2016 18:19:12 | 27/07/2016 16:09:08 | 3 | Communication Error | 3 - Medium | 27/07/2016 16:22:15
58 | Allotment: Add Application screen : User is unable to get the appropriate message for non mandatory fields. | Bug | Dhananjay Kaushik | Closed | 4 | 27/06/2016 18:52:24 | 18/07/2016 18:24:12 | 3 | Design Error | 3 - Medium | 18/07/2016 19:41:45
64 | MDM- Add Scheme: Issue in the fields Installment Money,Allotment Money,Lease Rent and Floor Area Ratio | Bug | Dhananjay Kaushik | Closed | 4 | 30/06/2016 13:47:05 | 18/07/2016 18:53:14 | 2 | Coding Error | 3 - Medium | 19/07/2016 13:13:11
67 | MDM: The edit scheme link is not working on view scheme screen. | Bug | Dhananjay Kaushik | Closed | 4 | 15/07/2016 11:25:13 | 15/07/2016 11:38:02 | 3 | Design Error | 3 - Medium | 15/07/2016 18:55:46
68 | MDM: Browser specific issue-Unable to add the property properly, as the total property cost is calculating as 0.( Working in Mozilla) | Bug | Dhananjay Kaushik | Closed | 4 | 15/07/2016 19:04:32 | 19/07/2016 11:26:48 | 2 | Coding Error | 2 - High | 19/07/2016 12:52:47
69 | UM: User mapping with role screen : The new added user with role is not displaying correctly in the grid. | Bug | Dhananjay Kaushik | Closed | 4 | 18/07/2016 13:23:29 | 18/07/2016 13:51:31 | 3 | Coding Error | 3 - Medium | 18/07/2016 13:52:51
70 | Allotment: User is unable to add any application for any new scheme added. | Bug | Dhananjay Kaushik | Closed | 4 | 18/07/2016 17:54:22 | 18/07/2016 18:02:00 | 4 | Coding Error | 3 - Medium | 18/07/2016 18:02:04
71 | Allotment: Suggestion- Add application- Under payment information section only those bank should be displayed which was added during the time of adding the scheme. | Bug | Dhananjay Kaushik | Closed | 4 | 19/07/2016 12:03:09 | 19/07/2016 16:49:43 | 4 | Coding Error | 4 - Low | 22/07/2016 19:49:20
74 | MDM: Manage Property- User is able to select the total area out of range from ( Area range) selected. | Bug | Dhananjay Kaushik | Closed | 4 | 19/07/2016 13:04:30 | 19/07/2016 19:28:58 | 2 | Coding Error | 3 - Medium | 21/07/2016 17:46:52
75 | MDM-Edit scheme-The status of any new scheme added should not be displayed as completed/Yes when the bank,cost and Rebate section is not added. | Bug | Dhananjay Kaushik | Closed | 4 | 19/07/2016 16:34:09 | 20/07/2016 14:47:44 | 3 | Coding Error | 3 - Medium | 21/07/2016 17:48:17
76 | MDM: Getting server error while clicking on Manage scheme- Unable to process with testing. | Bug | Dhananjay Kaushik | Closed | 4 | 19/07/2016 16:53:38 | 22/07/2016 23:08:36 | 3 | Coding Error | 2 - High | 23/07/2016 18:13:42
78 | MDM: Add scheme- User should not be able to add any scheme without completing all the sections( say-schedule of land development) | Bug | Dhananjay Kaushik | Closed | 4 | 19/07/2016 18:38:58 | 20/07/2016 14:46:52 | 2 | Coding Error | 2 - High | 21/07/2016 17:47:41
79 | MDM: For any new scheme unable to calculate the total property cost correctly and also the sector is not populating correctly while adding the property. | Bug | Dhananjay Kaushik | Closed | 4 | 20/07/2016 12:59:57 | 21/07/2016 19:42:51 | 4 | Coding Error | 2 - High | 22/07/2016 19:24:46
80 | MDM: Unable to add scheme with Department as Housing. | Bug | Dhananjay Kaushik | Closed | 4 | 20/07/2016 16:33:24 | 20/07/2016 18:49:13 | 2 | Coding Error | 2 - High | 21/07/2016 17:42:39
81 | MDM: Manage circle rate issue ( heading name missing)- User is unable to enter the data as per the formula (The Circle rate duration is not End date of circle rate = [Start date of new circle rate-1]) | Bug | Dhananjay Kaushik | Closed | 4 | 20/07/2016 17:17:31 | 21/07/2016 14:38:49 | 3 | Coding Error | 3 - Medium | 21/07/2016 19:01:02
90 | MDM: Add notification is not working. | Bug | Dhananjay Kaushik | Closed | 4 | 21/07/2016 18:33:42 | 26/07/2016 12:12:39 | 4 | Coding Error | 3 - Medium | 2016-01-08 16:25
92 | MDM: Add Property Screen- User is not able to add any property in case clicks on Add button twice. | Bug | Dhananjay Kaushik | Closed | 4 | 22/07/2016 13:43:46 | 22/07/2016 19:46:19 | 4 | Coding Error | 2 - High | 23/07/2016 18:19:20
93 | Allotment( Backlog) :Add Application: Duplicate application should not be created upon double click and also the Form should be unique department wise for any scheme. | Bug | Dhananjay Kaushik | Closed | 4 | 22/07/2016 16:23:15 | 26/07/2016 11:45:37 | 2 | Coding Error | 2 - High | 2016-01-08 17:27
95 | MDM: Add property screen: Add button gets disabled while adding a new property. | Bug | Dhananjay Kaushik | Closed | 4 | 23/07/2016 14:54:15 | 27/07/2016 12:58:50 | 2 | Coding Error | 2 - High | 2016-01-08 16:25
98 | MDM: Edit Refund - Getting server error while updating a refund. | Bug | Dhananjay Kaushik | Closed | 4 | 25/07/2016 17:23:08 | 26/07/2016 13:05:54 | 2 | Coding Error | 2 - High | 2016-01-08 16:26
106 | Add property screen: Getting server error while clicking on Add button and cancel button. | Bug | Dhananjay Kaushik | Closed | 4 | 27/07/2016 19:01:00 | 28/07/2016 12:05:15 | 1 | Coding Error | 1 - Critical | 2016-01-08 15:47
114 | Suggestion: The location section should not be available for housing department. | Bug | Dhananjay Kaushik | Resolved | 4 | 2016-03-08 16:06 | 2016-03-08 17:49 | 4 | Design Error | 4 - Low
159 | Add property: suggestion- The Property no Should not be zero( The Property should be unique for same department, sector & block ) | Bug | Naresh Kumar | Resolved | 4 | 2016-01-09 10:55 | 2016-12-09 15:42 | 3 | Communication Error | 4 - Low
Bug 29: | Add Scheme: The date format should be in MM/ DD /YYYY through out the application | Bug | Naresh Kumar | Resolved | 5 | 2016-02-06 | 19/07/2016 | 4 | Communication Error | 5 - Low