## Sheet1
ID | Title | Work Item Type | Assigned To | State | Iteration ID | Created Date | Resolved Date | Priority | Root Cause | Severity | Closed Date
59 | Allotment: Unable to test anything for Allotment - Getting server error. | Bug | Dhananjay Kaushik | Closed | 7 | 28/06/2016 12:43:35 | 28/06/2016 13:57:26 | 1 | Coding Error | 1 - Critical | 28/06/2016 16:04:49
60 | Allotment: Add application-User Should not be allowed to enter 0 as amount deposit through RTGS while adding any application. | Bug | Dhananjay Kaushik | Closed | 7 | 28/06/2016 15:14:40 | 19/07/2016 16:47:59 | 3 | Coding Error | 2 - High | 22/07/2016 19:51:36
61 | Allotment-Edit Application: User should be able to edit any application successfully. | Bug | Dhananjay Kaushik | Closed | 7 | 28/06/2016 15:44:22 | 29/06/2016 18:54:47 | 3 | Coding Error | 2 - High | 15/07/2016 19:20:06
62 | Allotment: View Application: User is not able to view the fields' value as entered for any application. | Bug | Dhananjay Kaushik | Closed | 7 | 28/06/2016 17:46:44 | 2016-02-08 15:50 | 3 | Coding Error | 3 - Medium | 2016-03-08 13:55
63 | Allotment: Bulk Application- Unable to upload the bulk application. | Bug | Dhananjay Kaushik | Closed | 7 | 29/06/2016 20:48:13 | 18/07/2016 12:32:44 | 3 | Coding Error | 2 - High | 19/07/2016 13:26:51
65 | Allotment: Manage Allotment- Issue in Add Allotment Details screen. | Bug | Dhananjay Kaushik | Closed | 7 | 30/06/2016 14:09:17 | 22/07/2016 23:41:14 | 1 | Coding Error | 2 - High | 23/07/2016 18:33:51
72 | Allotment: Refund-Manage refund screen : Getting server error while user click on View list under action column. | Bug | Dhananjay Kaushik | Closed | 7 | 19/07/2016 12:18:28 | 19/07/2016 16:00:38 | 3 | Coding Error | 3 - Medium | 22/07/2016 17:53:16
73 | Allotment: User is able to approve /reject on 'Allottee List Request' again and again. | Bug | Dhananjay Kaushik | Closed | 7 | 19/07/2016 12:27:01 | 27/07/2016 13:05:24 | 2 | Coding Error | 2 - High | 2016-01-08 17:37
82 | Allotment-The user should be able to see the bank which is added during during scheme while adding a new application. | Bug | Dhananjay Kaushik | Closed | 7 | 20/07/2016 17:59:13 | 27/07/2016 13:06:01 | 3 | Unknown | 3 - Medium | 2016-01-08 17:37
83 | Alotment: Random issue-Unable to view the schemes while adding any application. | Bug | Dhananjay Kaushik | Closed | 7 | 20/07/2016 18:03:12 | 27/07/2016 13:00:15 | 2 | Coding Error | 2 - High | 2016-03-08 18:20
84 | Allotment: Regression testing issues. | Bug | Dhananjay Kaushik | Closed | 7 | 20/07/2016 18:10:41 | 27/07/2016 17:02:46 | 2 | Coding Error | 2 - High | 2016-02-08 11:13
85 | Allotment- Edit Allotment Details: User is unable to edit the 'Installment Start Date' | Bug | Dhananjay Kaushik | Closed | 7 | 20/07/2016 19:01:15 | 22/07/2016 21:17:05 | 2 | Communication Error | 4 - Low | 23/07/2016 18:26:38
86 | Allotment: User is not able to reject any application also not able to approve when aprover give comments ( =characters) | Bug | Dhananjay Kaushik | Closed | 7 | 21/07/2016 11:33:11 | 21/07/2016 14:16:05 | 2 | Coding Error | 2 - High | 22/07/2016 19:47:35
87 | Allotment : Through out the application-The format and the print content should be properly aligned and should be displayed properly. | Bug | Mankaran Singh Kohli | Active | 7 | 21/07/2016 12:03:44 |  | 3 | Design Error | 2 - High
88 | Allotment: The approve list should be displayed department wise. | Bug | Dhananjay Kaushik | Closed | 7 | 21/07/2016 12:34:26 | 22/07/2016 10:41:14 | 3 | Coding Error | 2 - High | 22/07/2016 19:24:02
89 | Allotment: All the details as entered during adding a scheme should displayed correctly throughout the application ( ex- Block, Department- Commercial) | Bug | Dhananjay Kaushik | Closed | 7 | 21/07/2016 13:18:04 | 2016-02-08 13:23 | 3 | Coding Error | 3 - Medium | 2016-03-08 16:27
91 | Allotment: Notification is not working for Refund/Approve/Reject. | Bug | Dhananjay Kaushik | Closed | 7 | 22/07/2016 10:59:19 | 27/07/2016 17:51:45 | 2 | Coding Error | 2 - High | 2016-01-09 12:32
94 | Allotment: Doubts/ suggestions: allotment date should not be a past date of any scheme . | Bug | Dhananjay Kaushik | Closed | 7 | 22/07/2016 17:37:47 | 27/07/2016 17:52:01 | 3 | Communication Error | 4 - Low | 29/08/2016 17:30:11
96 | MDM: Unable to view the previous scheme on 'Manage Applications' screen when I create a new scheme and navigate till Manage Applications screen. | Bug | Dhananjay Kaushik | Closed | 7 | 23/07/2016 18:05:19 | 27/07/2016 13:06:18 | 1 | Coding Error | 2 - High | 2016-01-08 17:03
97 | Allotment: Draftr allottee list screen : Duplicate row gets displayed for the same scheme. | Bug | Dhananjay Kaushik | Closed | 7 | 25/07/2016 13:38:09 | 26/07/2016 18:31:52 | 2 | Coding Error | 2 - High | 2016-01-08 17:37
99 | Allotment:View Allotment : User is not able to view the fields' value as entered for any allotment. | Bug | Dhananjay Kaushik | Closed | 7 | 25/07/2016 18:05:00 | 26/07/2016 11:34:20 | 3 | Coding Error | 2 - High | 2016-01-08 17:29
100 | Allotment- Refund is not working- Getting server error. | Bug | Dhananjay Kaushik | Closed | 7 | 26/07/2016 12:21:20 | 26/07/2016 13:15:41 | 1 | Coding Error | 2 - High | 27/07/2016 17:32:57
101 | Allotment: Add Allotment Details- Getting server error while user clicks( twice) on Add button. | Bug | Dhananjay Kaushik | Closed | 7 | 27/07/2016 14:06:02 | 27/07/2016 17:51:39 | 2 | Coding Error | 2 - High | 2016-01-08 17:02
102 | Allotment: Allottee List Request screen : Duplicate RID should not be generated. | Bug | Dhananjay Kaushik | Closed | 7 | 27/07/2016 15:48:07 | 27/07/2016 17:33:56 | 2 | Coding Error | 2 - High | 2016-01-09 12:23
103 | Allotment: The Approved on date should be displayed as per the approval/ reject of any application. | Bug | Dhananjay Kaushik | Closed | 7 | 27/07/2016 16:03:18 | 27/07/2016 20:19:57 | 2 | Coding Error | 2 - High | 2016-01-08 17:11
104 | Allotment: Refunds - Unsuccessful Applicants- Unable to initiate refund for any unsuccessful applicants | Bug | Vishal Shukla | Active | 7 | 27/07/2016 16:56:56 |  | 3 | Coding Error | 2 - High
105 | Allotment: Unsuccessfull Applicant List Request - Getting error by clicking on approve button. | Bug | Dhananjay Kaushik | Closed | 7 | 27/07/2016 17:13:19 | 27/07/2016 17:36:37 | 4 | Coding Error | 2 - High | 2016-01-08 17:30
107 | Allotment: The company name is not displaying on manage application screen. | Bug | Dhananjay Kaushik | Closed | 7 | 2016-02-08 11:34 | 2016-03-08 19:07 | 3 | Coding Error | 3 - Medium | 29/08/2016 13:19:29
108 | Allotment: Edit Application/ Add application- An appropriate message should be displayed upon invalid entry for any fields. | Bug | Dhananjay Kaushik | Closed | 7 | 2016-02-08 11:55 |  | 4 | Specification Error | 3 - Medium | 2016-01-09 12:29
109 | Allotment: Edit allotment- Error message should not come while editing any allotment. | Bug | Dhananjay Kaushik | Closed | 7 | 2016-02-08 12:22 | 2016-02-08 16:17 | 2 | Design Error | 3 - Medium | 2016-01-09 12:26
110 | Allotment: The form number should be unique for a scheme department wise. | Bug | Dhananjay Kaushik | Closed | 7 | 2016-02-08 14:44 | 2016-04-08 17:19 | 3 | Coding Error | 2 - High | 2016-01-09 12:33
111 | Allotment: Draft Allottee list: The status is not changing as per the transaction ( approval/ reject) | Bug | Vishal Shukla | Active | 7 | 2016-02-08 15:43 |  | 3 | Coding Error | 2 - High
135 | Allotment: Property Details screen : Unable to view the Applicant Details (ex- Department Name -Housing) | Bug | Vishal Shukla | Active | 7 | 24/08/2016 17:47:56 |  | 3 | Coding Error | 2 - High | 15/09/2016