## Sheet1
ID | Title | Work Item Type | Assigned To | State | Iteration ID | Created Date | Resolved Date | Priority | Root Cause | Severity | Closed Date
112 | Allotment: Property Details- The allotment money Civil cost and property cost are not displaying as per the requirement. | Bug | Dhananjay Kaushik | Closed | 9 | 2016-02-08 18:03 | 2016-03-08 14:12 | 3 | Unknown | 3 - Medium | 2016-03-08 16:15
113 | Lease deed: User should not be able to “Add Lease Deed” when dues are available on Payments. | Bug | Ranjeet Singh | Closed | 9 | 2016-03-08 15:04 | 2016-03-08 17:24 | 2 | Coding Error | 3 - Medium | 2016-03-08 21:00
115 | Lease Deed: User is not able to find correct amount on Lease rent challan | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-03-08 19:12 | 2016-08-08 10:49 | 2 | Unknown | 3 - Medium
116 | Lease deed: Dues are not correct in payment schedule section. | Bug | Ranjeet Singh | Closed | 9 | 2016-04-08 15:54 | 2016-05-08 16:59 | 2 | Coding Error | 3 - Medium | 2016-08-08 16:19
117 | Lease Deed: Allotment money should be displayed instead Yes on checklist. | Bug | Vishal Shukla | Active | 9 | 2016-04-08 16:59 |  | 2 | Unknown | 3 - Medium
118 | Lease deed: Document required list should be available on the checklist pop up/ RID: 77 | Bug | Vishal Shukla | Active | 9 | 2016-04-08 17:05 |  | 2 | Unknown | 3 - Medium
119 | Lease Deed: User should not be able to select checklist date before allotment date | Bug | Ranjeet Singh | Closed | 9 | 2016-04-08 17:08 | 22/08/2016 13:18:01 | 2 | Coding Error | 3 - Medium | 24/08/2016 13:14:31
120 | Mutation: Add Mutation Request screen - User is not able to add the mutation request. | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 16:02 | 2016-05-08 16:12 | 2 | Coding Error | 2 - High
121 | Mutation: Add Mutation Request screen - User should not be allowed to send for approval of any mutation request to an admin who is not having right to that department. | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 16:32 | 2016-08-08 14:38 | 3 | Coding Error | 2 - High
122 | Mutation: View Mutation Request screen issue: RID and transfer date are not displaying as entered. | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 17:47 | 2016-08-08 14:45 | 4 | Coding Error | 3 - Medium
123 | Possession: User is not able to add possession entry. Application gets crashed. | Bug | Dhananjay Kaushik | Closed | 9 | 2016-05-08 19:02 | 19/08/2016 17:36:30 | 1 | Coding Error | 1 - Critical | 24/08/2016 14:24:29
124 | Possession: User should be able to add possession order for his department only | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:05 | 19/08/2016 17:37:50 | 2 | Coding Error | 3 - Medium
125 | Possession: User should not be able to add possession order for RID which has already added possession order and an alert msg should be generated. | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:08 | 22/08/2016 16:50:32 | 2 | Coding Error | 3 - Medium
126 | Possession: System should generate a message when user clicks on Add button on 'add possession order' page | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:11 | 22/08/2016 16:51:21 | 2 | Coding Error | 3 - Medium
127 | Possession: Wrong message is displayed and filled information is not reset when user selects select after selecting RID in the RID dropdown on 'Add possession order' page | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:14 | 22/08/2016 14:54:59 | 2 | Coding Error | 3 - Medium
128 | Possession : When area of a property is changed during possession, Area change column in grid contains ‘Yes’, else it should contain ‘No’ | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:18 | 26/08/2016 12:59:50 | 2 | Coding Error | 3 - Medium
129 | Possession: In case of company, • Signing Authority • Registered office not available | Bug | Ranjeet Singh | Closed | 9 | 2016-05-08 19:22 | 22/08/2016 13:28:21 | 2 | Coding Error | 3 - Medium | 25/08/2016 13:49:54
130 | Possession: Wrong message is displayed when user clicks on 'add' button on 'add bulk possession order' page after selecting scheme and department | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 19:34 | 26/08/2016 12:39:08 | 2 | Coding Error | 3 - Medium
131 | Lease deed: Lease deed execution date should always be after allotment date on add lease deed page. | Bug | Dhananjay Kaushik | Resolved | 9 | 2016-05-08 21:00 | 25/08/2016 10:39:00 | 2 | Coding Error | 3 - Medium
134 | Possession: Possession details are not captured on Add Possession Entry page. | Bug | Dhananjay Kaushik | Resolved | 9 | 24/08/2016 14:28:18 | 26/08/2016 20:29:26 | 2 | Coding Error | 3 - Medium
160 | Add lease deed: User is not able to to add lease deed. | Bug | Ajay Pratap Solanki | Active | 9 | 2016-01-09 13:24 |  | 2 | Coding Error | 1 - Critical