## Backlog Sprint
Sno | Changes | Description | Duration | Assigned To | Development Status | Requirement Status | Validation Status | Validation By | Comments | BA Team:Current Status (Pass/Fail) | Dkaushik:Current Status (Pass/Fail) |  | Comments
1 | Login Page | For internal users instructions should be removed |  |  | Fixed | na | Yes | Arun | Suggestion Alignment of comment "If you don't have Login, please contact Administration to login.". |  | Pass
|  | Functionality of "Forgot Password" should removed |  |  | Fixed | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
|  | Pop-up message to be displayed " Please contact your system administrator". | 9 hours | Shatrughna | Fixed | Updated User Story | Yes | Arun |  | Pass | Pass
|  | System Administrator would have option to "Reset" the password for the internal users. |  |  | Pending | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
2 | Role Name | Role Name (Eg: Admin 1) should not be displayed on the screen as shown on the top of current developed screen. |  |  | Fixed | na | Yes | Arun |  | Pass | Pass
3 | Masterdata | Department accordian> No. of Installemnt to be replaced with Maximum no. of Installment |  |  | Fixed | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
4 | Error Page | Standard error page should be shown. |  |  | Pending | na |  | Arun |  |  | Pass
5 | Activate/De-Activate Actions | On the grid "Activate" action would be shown if the role is deactivated. |  |  | Fixed | Updated User Story | Yes | Arun |  | Pass | Pass
6 | Scheme | Alternate "Edit Button" option should be provided when the user clicks on the Scheme Name in the grid under menu "Manage Scheme". |  |  | Pending | Updated User story and wireframe | Yes | Arun | The first section should be open by default | Pass | Pass
|  | Name of the Scheme should be displayed under the Label "View Scheme". |  |  | Fixed | Updated User Story | Yes | Arun | Name of the scheme ( As a heading) should be displayed while editing any scheme | Pass | Pass
|  | Details of the scheme (Start Date, End Date etc) can be edited, if the properties are not attached in it. |  |  | Fixed | Already updated | Yes | Arun |  | Pass | Pass
|  | Cost Accordian>The allotment money % and Installment money % should be equal to 100%. | 7 Hrs 15 mins | Ambrish | Pending | Updated User Story | Yes | Arun | This should be in Department section instead of cost section. | Pass | Pass
|  | Floor Area Ratio should be in percentage(<100) |  |  | Pending | na | Yes | Arun | This should be in Department section instead of cost section. | Pass | Pass
|  | Cost Accordian> Property types would be shown as per the departments selected. |  |  | Fixed | Updated User Story | Yes | Arun | it is working fine.< Due to zunk data in DB I am still able to view Flats as property type for the department Institutional) | Pass | Pass
|  | Bank Accordian> Branch Name to be replaced by Branch Address |  |  | Fixed | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
|  | Bank Accordian> Account Number: Alphanumeric(Field Level Validation) |  |  | Fixed | Updated User Story | Yes | Arun |  | Pass | Pass
7 | Manage Allotment | Department column to be added in the manage allotment grid. |  |  | Pending | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
8 | Validations | Earnest money (INR)should not be greater than allotment money (INR) |  |  | Pending | Updated User Story | No | Arun |  | Pass | Pass
|  | Units> Change the naming conventions (FIX----No. of units & PER------Percentage %) |  |  | Fixed | Updated User Story & Wireframes | Yes | Arun | Okay as per vishal sir : In data base only 3 chars will be allowed | Pass | Pass
9 | User Mapping | Search results should not be displayed in grid. | 8 hours | Mankaran | Pending | na | No | Arun | Application name and Role should be shown as per selection Search dropdown missing | Pass | Pass
10 | Manage Application | Add Application> On the personal information page CNC should be removed and field level validation (12 numeric) |  |  | Fixed | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
|  | Add Application>Demand Draft Number: Alphanumeric (Field level validation) |  |  | Fixed | Updated User Story & Wireframes | No | Arun | There are some items to be changed on Add Application form: 1) First name is written twice, Last name missing 2) Amount deposited is still text box, as per discussion it should be DDL 3) Alpha numeric validation is still not applied, it is still taking only numeric in DD field 4) Once application is added it is not reflecting grid. Unable to validate above as Amount deposit DDL not functioning | Pass | Pass
|  | Department column to be added in the manage application grid. | 3 hours | Naresh | Fixed | Updated User Story & Wireframes | Yes | Arun |  | Pass | Pass
11 | Change Password | Change Password option would be displayed on LHS navigation pane of page. |  |  | Fixed | na | Yes | Arun |  | Pass | Pass
12 | Change in Menu Name | Manage Admin Role & Manage Admin User should be replaced with "Manage Role" & "Manage User" respectively. These menu name should be changed in both Super Admin and Admin. |  |  | Fixed | Updated User Stories | Yes | Arun |  | Pass | Pass
|  | Check that area of property should be in the area range selected. |  |  | WIP |  |  | Arun | Browsing issue- Defect raised in TFS. | Pass | Fail | BUG84 and BUG 94
13 | Breadcrumb | Breadcrumb feature should be implemented in all modules. | 8 Hours | Anuj | Fixed | na | Yes | Arun | Not Functioning properly, Known Issues | Pass | Fail | BUG33
14 | Master Data | Add Circle Rate/Remove Circle Rate |  | Anuj/Naresh | Pending | Added New Userstory and Wireframe | No | Arun | Not developed | Pass | Pass
15 | User Management | Menu Mapping |  | Anuj/Naresh | Pending | Added New Userstory and Wireframe | No | Arun | Breadcrumb feature is not displaying in 'Application Users mapping with Role' screen. ( Login with Admin): As discussed with Dev team this functionaloty will be no more. | Pass | Fail
16 | Allotment | Auto Schedule for land development (Add/Edit/Remove) |  | Unassigned | Pending | Added New Userstory and Wireframe | No | Arun | Not developed | Pass | Pass
Extra Issues
| 1 | Masterdata>Manage Property>Edit Property | Alignment of fields on form |  |  |  |  | Ok

## Fixes
Items | Module | Development Status | Validation Status
No. of fields to be reduced in Department Grid (Alignment) | Scheme | Fixed | No Action
No. of Installment -> Max. No. of Installment | Scheme | Fixed | Pass
Decimal 2 digits in Department portion | Scheme | Fixed | Pass
Lease Rent not above 2 digits | Scheme | Fixed | Pass
Interchange Installment Money and Allotment Money fields' positions | Scheme | Fixed | Pass
Add % sign to FAR in Department and can't exceed 99% | Scheme | Fixed | Pass
Validations for all % fields | Scheme | Fixed | Pass
Quota value in % can't exceed 5 digits including decimal | Scheme | Fixed | Pass
If one quota is in %, all other Quotas should be in % too | Scheme | Wip | Pass
Quota value in FIX can't exceed 5 digits including decimal | Scheme | FIxed | Pass
Rebate -> Per -> 5 digits, INR -> 10 with decimals in both | Scheme | Fixed | Fail
Cost -> Property Type should be picked up on the basis of Department | Scheme |  | Pass
Cost -> Check duplicacy on the basis of first four fields instead of the first two fields | Scheme | Fixed | Pass
Add Property -> Total Area should not exceed the Area given in Scheme | Property | Fixed
Property -> Housing -> Floor, all others -> Area Range | Property | Fixed | Pass
Rates and amounts and areas should be in decimals -> upto 2 places | General | Fixed | Pass
Amounts related fields should always be on right of the textbox | General | Fixed | Pass
Earnest Money can't exceed Allotment Money in Housing case | Scheme |  | Pass
Allotment Money cannot exceed total property cost in case of housing | Scheme |  | Pass
Application -> Deposit Amount DDL -> values from Earnest Money in Scheme | Add/Edit Application | WIP | Fail
Bank Details -> Disable cascading DDL in case of Other in Bank Name DDL | Scheme | Fixed | Pass
Issue date of DD and RTGS Date should be between Scheme Start Date and End Date in Application | Add/Edit Application | Fixed | Pass
Start Date of Notification should be in between Scheme Start and End Date | Notification | Fixed | Pass
Scheme data -> make 1st Accordion editable | Scheme |  | Pass
Add Allotment Details -> Property No. not selecting on the basis of Scheme, Deptt, Form | Add Allotment | Not Start | Pass
Add Allotment Details -> Restrict characters in Area | Add Allotment | Fixed | Pass
Change order of fileds in Naresh's forms -> e.g. First Name and Middle Name should be in the same row |  | Fixed | Pass

## Sheet1
Changes | Description | Validation Status
Masterdata>Manage Property>Edit Property | Alignment of fields on form | Fail
User is logged of as following cases | When Super admin clicks on "Add User", user is logged out | Fail
| User clicks on edit on the manage scheme grid. User then clicks on home and is logged out. | Fail
| User views the scheme and click on alternate option of Edit button and is logged out. | Fail
Scheme>Edit>Back button> Error Page | User clicks on edit on the manage scheme grid. User then clicks on the back arrow and is shown error page. | Fail
Manage Scheme>Edit Property | User clicks on the edit option under manage scheme grid and no proper alignment is there on edit form. | Fail
Validation under Scheme | Allotment money cannot exceed total propety cost in case of housing | Fail
Error Page | Spelling mistake issue | Fail
Breadcrumb | Not functioning | Known Issue